## ProjectSchedule
PROJECT TITLE |  | Symptomatic Service - Demand Management Service Improvement
[Insert Center Name]
|  | Project Start: | 2020-07-01
|  | Display Week: | 1 |  |  | 2020-06-29 | [6 empty] | 2020-07-06 | [6 empty] | 2020-07-13 | [6 empty] | 2020-07-20 | [6 empty] | 2020-07-27 | [6 empty] | 2020-08-03 | [6 empty] | 2020-08-10 | [6 empty] | 2020-08-17 | [6 empty] | 2020-08-24 | [6 empty] | 2020-08-31 | [6 empty] | 2020-09-07 | [6 empty] | 2020-09-14 | [6 empty] | 2020-09-21 | [6 empty] | 2020-09-28 | [6 empty] | 2020-10-05 | [6 empty] | 2020-10-12 | [6 empty] | 2020-10-19 | [6 empty] | 2020-10-26 | [6 empty] | 2020-11-02 | [6 empty] | 2020-11-09 | [6 empty] | 2020-11-16 | [6 empty] | 2020-11-23 | [6 empty] | 2020-11-30 | [6 empty] | 2020-12-07 | [6 empty] | 2020-12-14 | [6 empty] | 2020-12-21 | [6 empty] | 2020-12-28 | [6 empty] | 2021-01-04 | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18
 | time axis 2020-06-29 to 2021-01-24
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-06-29 to 2021-01-24
Stage 1 Retrospective Audit
Task 1 - Review evidence to support intervention |  | 0% | 2020-07-01 | 2020-07-08 | 8
Task 2 - Collate and review Trust data to support intervention |  | 0% | 2020-07-01 | 2020-07-08 | 8
Task 3 - Allocate and secure Clinical and Admin time required for project |  | 0% | 2020-07-01 | 2020-07-08
Stage Gate 1 - Present at Trust Clinical Governance Team for Feedback & Buy-in |  | 0% | 2020-07-01 | 2020-07-08
Stage 2 Local Intelligence Gathering & Stakeholder Engagement |  | 0% | 2020-07-01 | 2020-08-20 | 51
Task 1 - Set up regular Cancer Alliance, Trust Senior Tanagement and key stakeholder Meetings including patient and public involvement |  | 0% | 2020-07-08 | 2020-07-10
Task 2 - Arrange to spend a day shadowing in a service known to employ this intervention |  | 0% | 2020-07-08 | 2020-07-15
Task 3 - Amend Gantt chart to meet individualised project needs |  | 0% | 2020-07-08 | 2020-07-15 | 8
Task 4 - Liaise with Trust Quality improvement team re QA and rigor and submit clinical audit request |  | 0% | 2020-07-08 | 2020-07-15
Task 5 - Liaise with CCG and Cancer Alliance to identify key primary care services open to visits and collaboration |  | 0% | 2020-07-08 | 2020-07-15
Task 6 - Develop or adapt template Introductory Letter to Primary Care stakeholders |  | 0% | 2020-07-08 | 2020-07-15 | 8
Task 7 - Arrange collective meeting to collaborate with stakeholders (Primary Care Leads, CCG, Cancer Alliance and identify key contacts. |  | 0% | 2020-07-13 | 2020-07-20
Task 8 - Collaborate with trust Safety & Quality lead (S&Q) for internal governance compliance |  | 0% | 2020-07-13 | 2020-07-20
Task 9 - Collaborate with trust IT to establish internal consistency (i.e. con to con referrals) with external form |  | 0% | 2020-07-13 | 2020-07-20
Task 10 - Collaborate with trust Clinical Patient Information Group (CPIG) to establish form compliance |  | 0% | 2020-07-13 | 2020-07-20
Task 11 - Collaborate with Pathology Services to sync Male bloods on referal form with IT pathology platform (i.e. ICE) |  | 0% | 2020-07-13 | 2020-07-20
Task 12 - Review and update referal forms |  | 0% | 2020-07-13 | 2020-07-20
Stage Gate 2 - Present project update to Trust Clinical Governance Team for Engagement & Feedback |  | 0% | 2020-07-13 | 2020-07-20
Task 13 - Send service change intro letter to primary care services via CCG |  | 0% | 2020-07-20 | 2020-07-27
Task 14 - Liaise with trust admin lead to adopt and/or adapt dataset for data collection |  | 0% | 2020-07-20 | 2020-07-27
Task 15 - Cross check to ensure service docs are aligned with relevant trust protocols, NICE Gudance and Nat. Guidance |  | 0% | 2020-07-27 | 2020-08-15
Task 16 - Ratify forms with CCG and ensure referal forms are NG12 formated |  | 0% | 2020-07-27 | 2020-08-15
Task 17 - Collaborate with trust Central Information Unit (CIU) to request rolling weekly reports of relevant clinics and sync with dataset for audit |  | 0% | 2020-07-27 | 2020-08-15
Task 18 - Collaborate with CCG to clarify trust response when non-compliant referral forms are received |  | 0% | 2020-08-27 | 2020-08-15
Stage 3 - Implementation of Referral Form - roll out via CCG |  | 0% | 2020-08-18 | 2020-08-18 | 1
Task 1 - Phase 1 Data Collection commences (First 4 weeks) |  | 0% | 2020-08-18 | 2020-08-15 | -2
Task 2 - Weekly data review and stakeholder collaboration |  | 0% | 2020-08-18 | 2020-08-15 | -2
Task 3 - Review - weekly referral numbers, urgent/nonurgent nos, breast pain nos and patient outcomes |  | 0% | 2020-08-18 | 2020-08-15 | -2
Task 4 - Cancer Alliance Milestone Update Meeting and presentation of data so far |  | 0% | 2020-08-22 | 2020-09-29
Stage Gate 3 - Present initial (4/52) data to trust Clinical Governance for Engagement & Feedback |  | 0% | 2020-08-22 | 2020-09-29
Task 5 - Phase 2 Data collection (First 8/52) |  | 0% | 2020-08-18 | 2020-10-06
Task 6 - Continue review of weekly referral numbers, urgent/nonurgent nos, breast pain nos and patient outcomes |  | 0% | 2020-08-18 | 2020-10-06
Task 7 - Liaise with Cancer Alliance and CCG to formalise primary care engagement and education opportunities to further optimise service improvement and cross service collaboration |  | 0% | 2020-09-30 | 2020-10-13
Stage 4 Phase 1 + 2 Evaluation |  | 0% | 2020-08-18 | 2020-10-06 | 50
Task 1 - Cancer Alliance Milestone Update Meeting and presentation of initial (8/52) data |  | 0% | 2020-10-06 | 2020-10-13 | 8
Task 2 - Write up initial findings |  | 0% | 2020-10-13 | 2020-10-27
Task 3 -Consider initial findings conference presentation and publication submission |  | 0% | 2020-10-13 | 2020-11-13 | 32
Stage Gate 4 - Repeat rows 34-36. Consider renewed Clinical Governance and Cancer Alliance collaboration for ongoing engagement & feedback as required |  | 0% | 2020-10-06 | 2021-02-18
Stage 5 Evaluation Phase 2 (At 6 Month Stage) |  | 0% | 2021-02-18 | 2021-02-25 | 8
Stage Gate 5 - Collaborate with key stakeholders to evaluate service improvement a 6 month stage and clarify the requirement for ongoing development or indication to embed current service change into routine practice |  | 0% | 2021-02-01 | 2021-02-24 | 24
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
2018-01-13
Note on H8: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.