## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
24/05 | 2024-05-15 | 7 | Board to hold a session on NICE’s commercial strategy once this has been further developed | PT/AW | 2025-05-01 | Agreed at September 2024 Board to defer this to Q1 2025/26 given the focus on planning for the Government’s spending review and the implications for NICE’s medium term financial plan. | Open | n/a
24/09 | 2024-10-07 | 6 | Further update on cyber security to be provided to the Board in December. | RV | 2024-12-01 | Update provided to the Board in December. | Closed | 2024-12-11
24/10 | 2024-09-25 | 6 | Further information to be provided to the Board on the income received outside of NICE’s core Grant-in-Aid funding, whether this is recurrent or non-recurrent, and progress in delivering the work associated with this funding. | PT | 2024-12-01 | Update provided to December Board seminar. | Closed | 2024-12-11
24/11 | 2024-09-25 | 6 | Board to receive an update on the approach for recognising guidance from other organisations in areas where NICE does not produce guidance, including using other organisations' guidelines to produce NICE quality standards. | JB | 2025-03-01 | Update scheduled for March 2025 public Board meeting. | Open | n/a
24/12 | 2024-09-25 | 8 | Board to receive further information on the outcome of the inquiry work into bullying and harassment and the planned next steps. | HB | 2025-03-01 | The bullying and harassment report has been written and is currently being reviewed. On completion of this review it will be shared with Board. | Open | n/a
24/13 | 2024-09-25 | 8 | Next equality report to reports include data on the overall composition of the advisory committees in addition to the characteristics of those applying and appointed to the committees in the previous year. | HB | 2025-09-01 | The data for this request isn't available due to the historic way NICE has engaged Committee members, mainly by local processes and more manual engagement and record keeping. Work is already underway to address this- centralising how we engage with members as well as how we embed them into the organisation to better effect. We are planning to be able to begin to report on these metrics and more from April onwards 2025. | Closed | 2024-12-11
24/14 | 2024-09-25 | 9 | Further research to be commissioned on societal preferences into the extent additional value should be given to treatments for severe diseases, supplemented by an interim qualitative analysis if feasible (e.g. through NICE Listens). | NC | 2024-12-01 | A tender specification for a NICE Listens deliberative public engagement project in 2025 is being prepared with a view to completing the project in March 2026. We are also preparing a proposal for a large scale study of societal preference regarding severity weighting for consideration by the DHSC R&D Committee. The proposal is anticipated to be completed in January 2025, and then completion of the study would be around 2 years after it is commissioned. | Closed | 2024-12-11
24/15 | 2024-09-25 | 10 | When the Board discusses the proposed implementation strategy this should set out the range of implementation support activities across NICE guidance across the system and outline the rationale for NICE’s proposed priorities, taking account of the work by other organisations. | CM | 2024-12-01 | Proposed approach to implementation presented to December seminar. | Closed | 2024-12-11