## Slide 1: Integrated Performance Report (IPR)
July 2024

## Slide 2: July 2024 IPR contents page
Section | Slide / chart number | Lead
Introductory points | 3 | Sam Roberts
Executive summary – highlights and escalation points | 4 | All ET
Summary of performance – Relevance | 5-6 | Jonathan Benger
Summary of performance – Timely and high quality | 7-9 | Sam Roberts
Summary of performance – Useable | 10-11 | Clare Morgan
Summary of performance – Demonstrable Impact | 12-13 | Clare Morgan
Summary of performance – Organisational Brilliance | 14-16 | Helen Brown
Finance including TA and NICE Advice income | 17-19 | Boryana Stambolova
Headline description of key projects | 20 | N/A - appendix

## Slide 3: July 2024 IPR – Summary points
The KPI figures included within this report reflect April and May figures - with the exception of Finance, which reports Q1 in full. A footnote has been included on each of the slides this applies to.
Board-level KPIs that do not have data to show progress have been included only as a footnote within relevant slides
Narrative updates, including milestones, have been captured to reflect latest progress at end of June.
The final slide provides a headline summary of the key projects that are referred to within this report, with the purpose of providing helpful supporting information for Board members.

## Slide 4: Executive summary on NICE Business Plan progress 2024-25 (July 2024)
Area | Current status | Key highlights and successes | Key challenges
Focusing on What is Most Relevant | Green | First Prioritisation Board met on 29 May – topic selection now integrated. The 'Forward view' of topic priorities (to be regularly reviewed in response to changes in system need and demand) has been finalised and will be published post general election. | Risk that the capacity in our current pipeline may not support the guidance we prioritise.
Providing High Quality & Timely Advice | Green | Incorporation of technology appraisals (TAs) into guidelines: 41 TAs incorporated into guidelines by end of May, and a further 59 are planned for Q2 - ahead of schedule against the overall target of incorporating 170 TAs in 24-25. Improving timeliness of guidance production and staff experience: We are seeking approval for this business case to be sought at July Board meeting. NICE/NHSE MedTech Rules-Based Pathway (RBP) consultation commenced on 23 May – due to conclude on 15th August. | Risk that the requirement to adequately engage stakeholders and ensure an appropriate level of expert input into the incorporation project could delay the overall timeline to incorporate Risk to achieving a strong business case for digitisation (ITSE) that gains investment approval Risk of difficulty reaching a policy position on the RBP that is acceptable to all stakeholders
Ensuring our Advice is Useable | Amber – due to ongoing clarification of programme interdependencies and decisions - being worked through in July | The new corporate website homepage launched in June and figures giving early insights of the impact of this will be included in the next Board report. Knowledge platform - collaboration with the Amazon Web Services (AWS) data science team to review the structure of NICE’s guidance content. This includes exploring use cases to inform our content structure and future knowledge platform requirements. | Alignment of activity in the structured recommendations project and the Digital Information Technology (DIT) knowledge spine activities has flagged critical interdependencies which are being resolved.
Demonstrable impact | Green | Priority topics agreed for health & care to guide insight and implementation work. | Risk of overcommitting to implementation work so will focus on priority areas, secure resource for VPAG implementation work and work as wider implementation function.
Brilliant organisation | Amber – due to significant under-spend | Values awards launched and first winners announced 5-year Equality & Diversity roadmap launched Increase in informal resolutions within employee relations in line with a Restorative Just Learning approach. ET succession planning activity completed for ET direct reports | Risk - NICE is £1.7m under plan at end of month 3 so that continuing trajectory would exceed 24-25 financial under-spend tolerance Issue - recruitment of Senior People Partner - challenge to find a suitable candidate, so reviewing requirements and revising recruitment approach
RAG rating key: C= complete; G= green; A= amber; R= red

## Slide 5: Relevance: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
NICE prioritisation board (PB) launched on 29th May, and this new approach has had support from sponsor teams in DHSC and NHSE.
The PB has been meeting every two weeks and is making decisions using the common prioritisation framework, and routing guidance development to the relevant guidance producing programmes
The prioritisation manual, thematic consultation comments and response, and the strategic principles for public health, social care and rare diseases have been published.
Live issues
Managing stakeholder expectations regarding what we prioritise (or not). Mitigation – continue to maintain engagement with key sponsor teams and utilise our wider insights from horizon scanning and system intelligence activities
Key activities for next month
Publish the first Prioritisation annual forward view.
Start publishing our prioritisation decisions on the prioritisation board webpage on the NICE website.
Key risks and mitigation
Risk – not having capacity in our current pipeline to produce the guidance we prioritise.
Mitigation -Prioritisation Board members from guidance developing teams will consider staff capacity and provide oversight of the guidance topic pipelines.

## Slide 6: Relevance: High-level summary of performance
Headline commentary on KPIs and milestones:
Prioritisation framework published. Prioritisation Board launched following shadow board period.
Prioritisation Board forward look has been postponed until post-general election
Recruitment timelines for horizon scanning roles may mean not all have started by end of Sept
NICE Business plan KPIs | KPI starting performance 23-24 | KPI performance target 24-25 | Actual YTD | Trajectory
% of positive decisions made by the Prioritisation Board that align to the key NHS and social care priorities described in our annual Forward View | N/A – new measure | 90% | N/A* data will start to be collected from Aug on a quarterly basis | N/A
% of responses to Regulation 28 reports, HSSIB safety recommendations and safety within specified and/or statutory timeframes | 90-95% | 95% | 95% | 
NICE Bus Plan Milestones | Due Date | RAG
Common prioritisation framework published following public consultation and agreement with system partners | Q1 | C
NICE’s Prioritisation Board launched | Q1 | C
Prioritisation Board’s forward look published | Q1 | A
Single horizon scanning function operational, linking with external providers | Q2 | A
Agreed an approach for recognising guidance from other organisations in areas where NICE does not produce guidance | Q2 | G
Consulted on any identified changes to routing criteria for Highly Specialised Technology Appraisals | Q4 | G
KPIs reflect April and May figures; There are a small number of KPIs measured via our annual reputation survey, and therefore they have not been included here. For ‘relevance’ there was one: “Agreement amongst our core audiences that NICE guidance is relevant in our reputation research survey in 2025”
RAG rating key: C= complete; G= green; A= amber; R= red

## Slide 7: Timely & High-Quality: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
NICE/NHSE medtech rules based pathway (RBP)
44 consultation responses received
Principles agreed and governance established on NICE-led RBP workstreams: NICE assessment, and Topic Selection
Improving timeliness of guidance production and staff experience:
Business case to be discussed at July Board
Roll out of digital tools to support topic management and agreeing requirements for committee management support tools
Incorporation of TAs into guidelines:
Positive feedback from stakeholders to plans for TA incorporation, and TAs fully incorporated into 19 guideline areas
Methods development:
Health inequalities methods audit completed informing next steps
Long list of potential topics for the HTA Lab proposed, with first topic agreed
Live issues
Improving timeliness and staff experience (ITSE) – internal resource to support MS project implementation. Mitigation – prioritisation of activity including focus on smaller pilot areas
Key activities for next month
  NICE/NHSE medtech rules based pathway (RBP):
  Identify current pipeline of potential technologies for prioritisation to test the RBP process
  Map the current process for topic selection and NICE assessment for RBP, and identify where it may not be fit for purpose
  Stakeholder engagement following the general election
Improving timeliness of guidance production:
MS Project on course to deliver a common approach to timeline management (part of topic management) by end of July
Planning tools de-commissioning technical review completed
Internal testing with the pilot solution built for committee management, and engagement with external associates to inform next steps.
Incorporation of TAs into guidelines:
Progress next batch of TAs for incorporation and develop clear expectations around how high-profile TA incorporations - where more flexibility might be required - should be managed
Further stakeholder engagement on integration (where health economic analyses updated) paused.
Key risks and mitigation
NICE/NHSE medtech rules based pathway:
Risk – Reaching a policy position on RBP that is acceptable to all stakeholders. Mitigation – Careful review of consultation responses, wide engagement, collaborative working with NHSE that acknowledges policy red lines early (e.g. NICE independence)
Improving timeliness of guidance production:
Risk – Achieving a feasible and timely solution to replace planning tools. Mitigation - continue to progress digital tools to support committee management, and customer relationship management (CRM)

## Slide 8: Timely & High-Quality: High-level summary of performance (1 of 2)
Headline commentary on KPIs and milestones:
KPI - Medicines improvement year on year between marketing authorisation and NICE recommendation - positive improvement but reflects low output numbers to date
Consultation on the med-tech rules-based pathway (RBP) has been extended to enable longer period for responses, and due to impact of general election
Retrospective incorporation of TAs into guidelines is on track and progressing as planned. Routine, prospective incorporation is now expected to begin in Q2 due to delays in publishing the selected TAs.
NICE Board KPIs (this slide are all NICE Board level KPIs ) | KPI starting performance 23-24 | KPI performance target 24-25 | Actual YTD | % improvement / decrease vs 23-24 performance
Medicines - Mean and median time between marketing authorisation and NICE recommendation (optimal and divergent) | 452 days (mean) 322 days (median) | Improvement on 23-24 baseline | 361 days (mean) 298 days (median) (N=8) | 20% improvement (mean) 7% improvement (median)
Medicines - Mean and median time between marketing authorisation and NICE recommendation (optimal) | 36 days (mean) 43 days (median) | 90 days (mean) 90 days (median) | 70 days (mean) 70 days (median) (N=1 ) | 94% deterioration (mean) 63% deterioration (median) NOTE: only one data point
Medicines - Mean and median time between marketing authorisation and NICE recommendation (divergent) | 540 days (mean) 365 days (median) | Improvement on baseline 23-24 | 402 (mean) 336 (median) (N =7) | 24% improvement (mean) 13% improvement (median)
Medicines - Improvement year on year in optimal topics as a % of all medicines’ appraisals | 16.5% | Improvement on 23-24 baseline | 12.5% | -4 percentage points
KPIs reflect April and May figures
NICE Board Milestones | Date | RAG
Start routinely incorporating relevant medicine technology appraisals in guidelines | Q1 | A
Understood baseline and opportunities for improvement in guidance producing processes | Q2 | G
Rolled out digital tools that support planning and identified future planning/scheduling needs | Q3 | G
Aligned and digitised some key steps in guidance producing processes | Q4 | A
Reviewed the use of the severity modifier in medicines evaluation and identified remedial actions if needed | Q2 | G
Updated methods for assessing health inequalities in guidance production | Q4 | G
Expanded HTA Lab capacity in line with new VPAG funding and delivered insightful outputs supporting high quality guidance | Q4 | G
Launched 8 Late-Stage Assessment topics | Q4 | G
Consulted (with NHSE) on a medtech rules-based pathway | Q1 | G
RAG rating key: C= complete; G= green; A= amber; R= red

## Slide 9: Timely & High-Quality: High-level summary of performance (2 of 2)
NICE Board KPIs | KPI starting performance 23-24 | KPI performance target 24-25 | Actual YTD | % improvement / decrease vs 23-24 performance
HealthTech - Mean and median time to publish HealthTech guidance | Mean: 490 days Median: 402 Days | Improvement on 23-24 baseline | Mean: 426 days Median: 419.5 days (N=9) | 13% improvement (mean) 4% deterioration (median)
CfG – % of quality standard updates published alongside guideline updates | N/A | 30% | N/A | 
% of TAs retrospectively incorporated by end of 24/25 | 0 | 33% (170 out of 517) | 8% (41) | 41 achieved by end of May against target of 42 for Q1
KPIs reflect April and May figures; Two KPIs have not been included here:
1) “Mean and median time to produce new guideline and guideline update” - data is being captured to establish a baseline for future measurement in 25-26;
2 “New NICE guidance within topic suites published within 6 months of Prioritisation Board's decision to update” - baseline data will start to be collected from August, and will be captured on a quarterly basis

## Slide 10: Useable: Exception report
RAG rating:
Amber
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
The new corporate website homepage has launched
In finalising work packages to create a structured recommendations framework, content governance and the foundational work to develop a digital knowledge platform, we have identified a number of interdependencies and decisions which are being worked through in July.
Agreed the alignment of structured recommendations for Medicines TAs with all of the Centre for Health Technology Evaluation (CHTE) directorate, ready for legal review.
Knowledge platform - the collaboration with Amazon Web Services (AWS) continues, to review the structure of NICE’s existing guidance content, including use of a semantic data modelling approach to enable componentisation.
Live issues
During the pre-election period no new content could be published on the corporate site. This was anticipated to impact the number of guidance clicks KPI from the corporate site. Mitigation - being actively monitored.
Key activities for next month
Develop remaining website page templates and scheduling of content for phased migration
Develop the structured recommendation model for guidelines
Knowledge platform - joint workshops with NICE exec and senior leaders to identify and understand interdependencies in foundational work to enable procurement and build from Sept
Key risks and mitigation
RISK There is a risk that changes made to the structure and language of recommendations will not align with guidance producing centres methods and culture and are not implemented consistently.
MITIGATION working with guidance teams to understand the impact on non-compliance on our users needs and their ability to use guidance to get the best care to people fast.
RISK Interdependencies in plans not identified and addressed so foundational work to move towards a content enabled, product organisation does not progress
MITIGATION Programme management of the useable programme actively manages all foundational aspects, accountability, risk management, resource allocation and independencies to ensure we meet this objective

## Slide 11: Useable: High-level summary of performance
Headline commentary:
It is too early to provide an indicator of performance for some KPIs shown below, due to the delay in the launch of the new corporate website which went live in June. The figures shown for users accessing guidance content include visits to guidance, advice and indicators. The baseline/comparator provided includes the equivalent months last year, as well as the rolling annual figure. The rolling annual figure will add greater value from the next report in September, when that will show the total figure from April-August, alongside the more specific figures for the latest two months in that period.
While the business plan milestones for Q4 are on track, we are tightly manging sub milestones to ensure we mitigate arising risks and interdependencies.
Business plan KPIs | KPI starting performance 23-24 | KPI performance target 24-25 | Actual YTD | % Increase vs 23-24
No of users accessing NICE website for guidance and advice | 3.241 million (baseline – Apr + May 23’) | Increase on equivalent calendar months from 23-24 | 3.388 million (Apr + May 24) | +4.5%
 | 18.278 million (Full year) | Increase on 23-24 | As above | N/A
Clicks on guidance products from the NICE corporate website (monthly figures) | 15.3 million (baselined Apr + May 23) | 17.6 million (15% increase from equivalent months in 23-24) | 14.4 million (Apr + May) | -6%
 | 83.2 million (Full year) | 95.7 million (15% increase in full year) | As above | N/A
Bus Plan Milestones | Due Date | RAG
Complete migration to new corporate website | Q4 | G
Complete proof of concepts with semantic data model to inform next steps of knowledge platform | Q2 | G
Agree standardised wording and structure for recommendations | Q4 | G
Launch a new content governance process | Q4 | G
KPIs reflect April and May figures; There are a small number of KPIs measured via our annual reputation survey, and therefore they have not been included here. For ‘Useable’ there are two: “No of users accessing NICE website for guidance and advice” and “Agreement among our core audiences that NICE guidance is useable”
RAG rating key: C= complete; G= green; A= amber; R= red

## Slide 12: Impactful: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Governance
Sub Programme Board governance structure established to ensure delivery, including impactful oversight group.
Delivery
Priority topics agreed to guide insight and implementation work (maternity, dementia, cardiovascular disease, weight management, and respiratory). These will then be used to guide development of the metrics that form the core impactful KPI about proportion of measures showing improvements in uptake.
Longlist of priority partners currently being collated to amplify NICE guidance
System intelligence - quarterly reporting of intelligence gathered is in place.
A policy for remuneration of non-staff involvement and engagement activity has been agreed.
Live issues
N/A
Key activities for next month
Longlist of priority partners to be refined and agree definition of “partnership” in context of implementation
Provide routine updates on national uptake in core areas covered by uptake data directory
Map strategic partners to priority topics to amplify guidance impact
Establish process to measure cumulative impact of NICE guidance
Develop approach to coordinating intelligence across insight and measurement functions
Key risks and mitigation
Risk - resource pressure on system partners may limit their capacity for what they see as discretionary activities. Mitigation - ensure priorities are relevant to system partners and seen as a contributing medium/long term solution to their pressures
Risk - there is a risk we raise expectations about increasing levels of all guidance uptake with the KPI about uptake measurement. Mitigation - careful communications around prioritised areas.
Risk - there is a potential risk that we overcommit implementation work. Mitigation - focus on priority areas, secure resource for developing implementation toolkits (in line with our commitments under the Voluntary Pricing, Access and Growth agreement) and work as a wider implementation function across NICE.
Risk - interdependencies with I&P, DIT and communications directorate need to be effectively managed to achieve objectives. Mitigation - establish clear requirements as part of work programmes which account for existing plans.

## Slide 13: Impactful: High-level summary of performance
Headline commentary:
KPIs: Work during 2024/25 will establish a baseline for 2 of the KPIs below (improvements in uptake and favourability amongst VCS organisations). The two KPIs about implementation support and priority areas will start to show progress over the next few months.
Much of the work under the impactful work programme is focused on delivery in a small set of priority areas. The most important task to date has been to develop a longlist of priority topics and then refine this into a shortlist for agreement.
Business plan KPIs | KPI starting performance 23-24 | KPI performance target 24-25 | Actual YTD | Trajectory
Proportion of agreed priority guidance measures showing an improvement in national uptake (health and care system priority areas, populations with identified health inequalities, areas that matter most to people and the communities). | N/A Baseline to be established during 24/25 | N/A | N/A | N/A
All agreed priority areas have targeted implementation support package in place | 0 | 5 | 0 *In line with expected milestones | 
New partnerships (including VCS organisations) to amplify the impact of NICE guidance in agreed priority areas. | 0 | 5 | 0 *as above | 
Bus Plan Milestones | Due Date | RAG
Developed and implemented a fairer payment policy for involvement and engagement activity | 30 June 24 | C
Routine reporting of prioritised uptake measures in place | 31 July 24 | G
Joint plans in place to amplify the impact of NICE guidance through priority partnerships | 30 Sept 24 | G
4 implementation support packages initiated to address agreed priority areas | 30 Sep 24 | G
Programme of shared learning in place, connecting practitioners and commissioners to implementation best practice | 30 Nov 25 | G
Developed and tested impactful approaches for involving people and communities in developments in all new prioritised guidance | 31 Mar 25 | G
KPIs reflect April and May figures; There are a small number of KPIs measured via our annual reputation survey, and therefore they have not been included here. For ‘Impactful’ there is one: “Overall favourability towards NICE amongst VCS orgs”
RAG rating key: C= complete; G= green; A= amber; r= Red

## Slide 14: Brilliant organisation: Exception report
RAG rating:
Amber
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Values awards launched and first values winners announced
5-year Equality & Diversity roadmap published.
All relevant Employee Relations and Unisons colleagues trained in Restorative, Just Learning Approach for dealing with conflict resolution - increase in informal resolution. Partnership with Unison strengthened - members now trained in consistency checking and job matching.
Commenced full process review including launching the new streamlined starters, changes and leavers forms, cutting time to completion drastically and making space for leaders to lead more.
Vacancy panel now ceased in its old form. This will transition to being relevant Exec led, People Team and Finance as approvers in Trac, speeding up but not compromising rigour.
The reputation research project is complete. Findings are being reported and plans to address these being rolled out.
Staff Survey now closed- results and updates to be shared at the end of July with Exec colleagues.
Successful highly rated independent ESR standards review.
Live issues
NICE is £1.7m under plan at end of month 3 – hence the overall amber rating. Mitigation approaches are set out within Finance section on slide 17.
Senior People Partner recruitment - challenging to find a suitable candidate. Mitigation - reviewing requirements and revised recruitment approaches.
Job Evaluation - issue of speed caused by increased volumes. Mitigation – train more volunteers and update templates to support.
Key activities for next month
Slot at next NICE Board drop-in for Restorative, Just Learning Approach
Business case to build continuous quality improvement capacity and capability
Key risks and mitigation
Risk - Operational pressures impacting pace of delivery of Project Nova (People team transformation). Mitigation:
Ongoing prioritisation of activity
Continuation of recruitment
Review and progression of resolution for operational issues
Risk - RAG status for overall cyber security posture of NICE continues to be “Red” but with an improvement in trend. There is now strong confidence that we will meet the target mitigated risk score of 16 by end of Q4 2024-2025 at the latest.

## Slide 15: Brilliant organisation: High-level summary of performance
Headline commentary: Amber rating for financial position. There are 3 key factors leading to this KPI being reported as red: Strong performance for TA and NA income, a higher than planned vacancy rate, plus uncommitted reserves – means overall NICE is £1.7m under plan at end of month 3 and therefore need to consider plans for in year non-recurrent investments. Manchester office move is rated as amber due to staff sickness – this is being mitigated by reprioritising resource to maintain progress.
NICE Business plan KPIs | KPI starting Performance 23-24 | KPI Performance target 24-25 | Actual YTD | % Increase vs 23-24
Media coverage of NICE that is positive in sentiment | 80% | 80% | 90% | +10 percentage points (pp)
Media coverage that is generated by NICE includes at least one NICE key message | 54% | 60% | 56% | +2pp
Representation of ethnic minority, disabled and LGBTQ+ colleagues at all levels | Ethnic 18.21​% Disabled​ 9.49% LGBTQ+​ 8.34% | Ethnic 20.3% Disabled 10.44% LGBTQ+ 9.17% | Ethnic 19.3% Disabled 9.8% LGBTQ+ 8.51% | +1pp +0.3pp +0.2pp
Number of informal resolutions | 21 | 31 (50% increase) | 11 | +214%*
Financial position (deficit and surplus) | No deficit, Surplus <£1m (Achieved) | No deficit, Surplus <£1m | -£1.7m | 
NICE Bus Plan Milestones | Due Date | RAG
Launched a new Equality, Diversity and Inclusion Roadmap including new objectives to improve staff experience and representation | Q1 | C
Rolled out Power-BI enabled detailed financial forecasting and scenario planning to increase accuracy of forecasts and engage operational teams | Q2 | G
Fully embedded finance business partnering to improve financial input into directorate decisions | Q3 | G
Completed a successful office move to our new Manchester office | Q3 | A
Leadership competencies implemented with initial review and feedback provided for all leadership teams | Q3 | G
KPIs reflect April and May figures with exception of financial position There are a small number of KPIs measured via our annual reputation survey, and therefore they have not been included here. For “Org Brilliance” there is one: “Overall favourability towards NICE amongst our core audiences”
RAG rating key: C= complete; G= green; A= amber; R= red
*Based on number achieved in 2 months (5.5 per month) compared to average 23-24 trajectory of 1.75 per month

## Slide 16: Appendix to Brilliant organisation
 | Target | Comparator/ baseline | YTD | % improvement or decrease | Add comment why target not met: provide reason, anticipated publication date/month | RAG
Sickness rate - overall | 3% | 3% | 2.78% | 0.2 percentage point (pp) improvement |  | G
Total turnover rate | N/A | No baseline | 12.03% |  |  | N/A
Voluntary turnover | N/A | No baseline | 7.67% |  |  | N/A
Non voluntary turnover | N/A | No baseline | 4.36% |  |  | N/A
FOIs | 90% of FOIs responded to with 20 working days | 90% | 97% | 7pp improvement | Target being exceeded | G
Parliamentary questions | 90% of Parliamentary Questions responded to within the requested time frame | 90% | 100% | 10pp improvement | Target being exceeded | G
Payment compliance | >95% invoices paid within 30 days of calendar month-end | 96% | 98.1% | 2.1pp improvement | Target being exceeded | G
Complaints | 80% of complaints acknowledged and responded to within 20 working days | 100% | N/A | N/A | No complaints received and due for response. | G
KPIs reflect April and May figures
RAG rating key: C= complete; G= green; A= amber; R= Red

## Slide 17: Financial performance as at 30 June 24 and Full year outturn
 | YTD budget £000 | YTD actual £000 | YTD variance £000 | Annual budget £000 | Estimated outturn £000 | Variance £000
Pay | 14,901 | 14,218 | -683 | 61,479 | 60,933 | -545
Non-pay | 5,970 | 5,461 | -509 | 26,928 | 27,716 | 788
Income | -6,793 | -7,291 | -498 | -27,206 | -28,299 | -1,093
Total | 14,077 | 12,388 | -1,690 | 61,201 | 60,351 | -850
YTD Financial performance
As at the end of June we are underspent by £1.7m. The underspend is driven by (1) Pay: actual vacancy rate of c8% vs. planned vacancy factor of 2.5%; (2) reserves not being drawn against year to-date and contingency not being utilised; and (3) higher income from medicines evaluation.
Full year forecast - scenarios
Assumption | £'000 | Likelihood | Comments | Range
Pay Award | 500 | M | Additional pay award over budget 2% | £0 - £1m
Dilapidations | 1,000 | H | Absorb the final, agreed dilapidations cost for Manchester office closure | £0 - £2.5m
DIT investment funds | 1,300 | M | Budget set aside to address tech debt and investment in digitisation. | £0 - £1.3m
Improving timeliness programme | 500 | M | Business case for continuous quality improvement and programme management support | £0 - £0.5m
Tech Debt | 350 | M | Bring forward estimated tech debt investment from 25/26 | £0 - £0.4m
Redundancy costs (23/24) | 690 | H | Absorb cost from org changes completed in 23/24. | £0.7m
Rent Review | 200 | M | Backdated rent review | £0 - £0.2m
Total | 4,540 |  |  | 
Full year forecast
Current FY forecast is £0.85m underspend. The forecast outturn includes assumptions about material expenditure in several areas totalling £4.5m (see table on the left). In a downside scenario there is a risk of a significant underspend if these costs do not materialise.
Project funding
In addition to baseline funding, we are expecting approximately £5m of project funding to include funding from the Office for Life Sciences (£2.2m) and the DHSC MedTech directorate (£1.5m) to support the growth of our HealthTech guidance, and the first year of ringfenced funding from the VPAG life sciences investment fund to support medicines uptake. Progress on deliverables for each funding stream are on track, with small underspends in quarter 1 due to staff turnover.

## Slide 18: TA-HST programme – finance position M3 (June) 24-25
Spend category | YTD budget £000 | YTD actual £000 | YTD Variance £000 | Annual budget £000 | Estimated outturn £000 | Estimated outturn variance £000
Pay | 2,856 | 2,792 | (64) | 11,598 | 11,486 | (112)
Non-Pay | 849 | 846 | (3) | 3,396 | 3,392 | (3)
Expenditure total | 3,705 | 3,638 | (67) | 14,994 | 14,878 | (116)
Income | (3,002) | (3,579) | (577) | (12,009) | (13,037) | (1,028)
(Surplus)/Deficit | 703 | 59 | (644) | 2,985 | 1,840 | (1,144)
Chart: TA HST income and costs - cumulative
| 45383 | 45413 | 45444 | 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717
Plan (£12m) | 1000.75 | 2001.5 | 3002.25 | 4003 | 5003.75 | 6004.5 | 7005.25 | 8006 | 9006.75 | 10007.5 | 11008.25 | 12009
Most-likely | 1060.5032 | 2025.9767 | 3578.9767 | 4653.7332 | 5496.7837 | 6678.9034 | 8060.9408 | 9183.4048 | 9625.67 | 10590.642 | 11567.363 | 13037.2679
Full-cost recovery | 1209.661 | 2436.6332 | 3663.7762 | 4902.228 | 6140.6797 | 7379.1315 | 8617.5833 | 9856.035 | 11094.4868 | 12332.9385 | 13571.3903 | 14982.7571
YTD performance is £0.6m better than plan reflecting a prior year discount adjustment (ca. £0.25m) along with higher throughput, better sales mix and pay underspend. This means that YTD the programme has required £644k less Grant-in-Aid funding.
Full year forecast income is £13m against a target of £12m, generating a forecast surplus of £1.1m. This reflect the full year effect of the discount adjustment (£0.4m) along with better sales mix.
The income forecast assumes a throughput of 80 units (the equivalent of 80 full STAs) this year and factors in historical drop-out rates.
Year-to-date, the programme has recovered 91% of its costs, excluding the effect of the prior year adjustment. Full-year cost recovery is forecast to be 88%, compared to 79% in 23-24.
The programme is not expected to utilise the c£400k contingency set aside in reserves.
*dashed lines denote forecast figures

## Slide 19: NICE Advice– Month 3 and FY 24-25 Forecast
NICE Advice has generated a YTD deficit of £44k. The full year forecast is for NICE Advice to achieve a breakeven position.
The FY forecast is based on identified revenue of £1.9m, agreed sales targets of £1.9m and gross expenditure of £4.35m.
OLS funding for staff and pilot project delivery totals £546k for the year.
The outturn includes a £1,182k contribution to overheads and use of NICE IP.
The cumulative contracted and pipeline revenue + IDAP line represent currently identified opportunities, which will increase as further sales are secured during the year.
Chart: NICE Advice 2024-25 Cumulative Forecast
| 45383 | 45413 | 45444 | 45474 | 45505 | 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717
Cumulative YTD Total income | 389512.56 | 666274.56 | 900036.75
Cumulative YTD Expenditure | 295158.5 | 596200.1 | 944311.42
Cumulative Forecast Expenditure | 944311.42 | 1278006.6367 | 1632801.8533 | 1995597.07 | 2358392.2867 | 2721187.5033 | 3083982.72 | 3446777.9367 | 3809573.1533 | 4222536.37
Cumulative Planned Sales Targets + IDAP | 900036.6 | 1327282.54 | 1792452.17 | 2057955.59 | 2680327.24 | 2936429.29 | 3201477.88 | 3483685.21 | 3775319.44 | 4198952.44
Cumulative Contracted and Pipeline Revenue + IDAP | 900036.6 | 1111764.43 | 1309163.97 | 1548093.34 | 1737014.49 | 1878177.38 | 2011206.72 | 2123648.26 | 2184808.27 | 2357025.15

## Slide 20: Headline description of key projects to deliver NICE aims
NICE aim | Project name | Project headline description
Timely and High-Quality Guidance | Rules Based Pathway (RBP) | Establishing the rules and principles on which NICE and NHS England will work in partnership to evaluate, commission and fund medical technologies
 | Improving Timeliness and Staff experience (ITSE) | Improved timeliness by standardising and improving processes across guidance producing centres, through the use of digital tools and continuous improvement approaches
 | Incorporation of TAs into guidelines | Inclusion of medicines and healthtech recommendations within guidelines to make NICE guidance more useful and useable
Useable | Content governance and Structured recommendations | Create shorter more structured recommendations which can be integrated across different types of guidance Revise the governance used to write all guidance products so are centred around users.
 | Knowledge platform | Procure and implement knowledge platform which structured content will be migrated to.
Impactful | Measurement uptake | Measure uptake of our guidance and use that data to ensure NICE focuses on our priorities.
 | Amplify priority partnerships | Work closely with critical stakeholders who can amplify our guidance in priority areas to help get the best care to patients fast.
 | Targeted implementation support | We will use implementation science to focus on system priorities populations with identified health in equalities and other areas that matter most to people and communities.
 | Public involvement best practice approach | Implementing a new way to reach the right members of the public at the right time in the right way to increase uptake of guidance and support getting the best care to people fast.