## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
24/05 | 2024-05-15 | 7 | Board to hold a session on NICE’s commercial strategy once this has been further developed | PT/AW | 2025-09-01 | Agreed at September 2024 Board to defer this to Q1 2025/26 given the focus on planning for the Government’s spending review and the implications for NICE’s medium term financial plan. | Open | n/a
24/11 | 2024-09-25 | 6 | Board to receive an update on the approach for recognising guidance from other organisations in areas where NICE does not produce guidance, including using other organisations' guidelines to produce NICE quality standards. | JB | 2025-03-01 | Update presented to March 2025 public Board meeting. | Closed | 2025-03-19
24/12 | 2024-09-25 | 8 | Board to receive further information on the outcome of the inquiry work into bullying and harassment and the planned next steps. | HB | 2025-03-01 | The report has been written and shared with the Board. | Open | n/a
24/16 | 2024-12-11 | 6 | Board to be briefed on the findings from the OHE report on societal preferences and the implications for the severity modifier | NC | 2025-03-01 | Briefing provided to the March Board seminar | Closed | 2025-03-19
24/17 | 2024-12-11 | 8 | Wording around research only recommendations in the HealthTech manual to be reviewed to clarify this means research in the context of a formally approved study. The process for reconsidering a research only recommendation in light of new data to be clarified and added to the manual (including in the decision making flow chart) to make clear that this is may not be the end state for an innovative technology | MC | 2025-01-01 | Text in the manual was updated to give more explanation about the meaning of a research recommendation. The consultation on the manual, which closed on 6 March, was used to check understanding and get stakeholder feedback on this wording. The text in the manual was also updated prior to the consultation to clarify how technologies can be reconsidered by NICE after initial guidance. | Closed | 2025-03-19
24/18 | 2024-12-11 | 8 | The revised standardised wording for recommendations across NICE’s TA/HST and HealthTech programmes to be circulated to the Board for information. | CM | 2025-03-01 | Wording circulated to the Board. | Closed | 2025-03-19
24/19 | 2024-12-11 | 10 | Board to be briefed on the implications for NICE of the outcomes of the review of patient safety across the health and care landscape. | JB | TBC | Awaiting publication of the review of patient safety across the health and care landscape led by Dr Penny Dash. | Open | n/a
24/20 | 2024-12-11 | 13 | PT to engage further with DHSC to explore the likelihood of future changes to NICE’s delegations. | PT | 2025-03-01 | Regular meetings held with ALB and DHSC directors of finance which provide the opportunity to gain insight into potential changes to spend controls. Any potential changes which are likely to impact NICE's ability to deliver its business plan will be highlighted to the Board. | Closed | 2025-03-19