## Slide 1: Integrated Performance Report (IPR)
March 2025

## Slide 2: March 2025 IPR contents page
Section | Slide / chart number | Lead
Executive summary – highlights and escalation points | 3 | All ET
Summary of performance – Relevance | 4-5 | Jonathan Benger
Summary of performance – Timely and high quality | 6-8 | Sam Roberts
Summary of performance – Usable | 9-10 | Clare Morgan
Summary of performance – Demonstrable Impact | 11-12 | Clare Morgan
Summary of performance – Organisational Brilliance | 13-14 | Helen Brown
Finance and commercial update | 15 | Pete Thomas
Appendix to Brilliant Organisation | 16-17 | N/A - appendix
Headline description of key projects | 18 | N/A - appendix

## Slide 3: Executive summary on NICE Business Plan progress 2024-25 (March 2025)
Area | Current Status | Key highlights and successes | Key challenges
Focusing on What is Most Relevant | Green | We will present the refined HST criteria and thematic responses to stakeholder comments at the NICE board meeting on 19 March. We have started engagement with DHSC and NHSE regarding co-creation of an improved process for funding variation requests. We will present our approach for the interim forward view at GE on 11 March. Positive safety team engagement with MHRA on a range of topics to support a number of ongoing issues in relation to Regulation 28 coroner reports and forthcoming Drug Safety Updates. We have integrated Interventional Procedures topic selection reporting into the NICE Prioritisation Board | Dealing with challenge to our refined HST criteria at the public board meeting on 19 March and subsequently Complexity of clarifications sought following prioritisation decisions especially Highly Specialised Technology routing decisions.
Providing High Quality & Timely Advice | Green | Timeliness: All 4 service project teams are testing improvement ideas. Preparation for the commencement of the Content Creation and Guidance Production Services in early 25/26 is also underway Methods: Good engagement and largely positive comments from health inequalities modular update consultation. The Modular update Selection and Oversight Panel prioritised EQ-5D-5L adoption and surrogate endpoints for modular updates. New HealthTech manual has been published for consultation. Incorporation of TAs: Remain on track to deliver over 170 TA incorporations by Q4 (180 planned). Significant stakeholder engagement with ABPI, DHSC/NHSE & Board Rules Based Pathway: Meeting held with devolved nations to identify areas of collaboration. NIHR and OLS have joined NHSE/NICE programme board. Supported drafting of the policy outline for the 10 Year Plan. Late-stage assessment: All 8 pilots have been through committee and 6 pilots have been through public consultation. | Timeliness: Challenges with staff capacity to test and scale change ideas. Office move and server availability continue to cause delay to reporting from MS Project Online and connectivity to data in other systems. Methods: Continuing to monitor the feedback from the severity modifier. Incorporation of TAs: Teams continue to face capacity challenges as work intensifies and complexity of incorporation topics increases. Rules Based pathway: Requires alignment with the 10 Year Health plan and spending review so may need to adapt approach when those policies conclude. Late-stage assessment: Stakeholder management
Ensuring our Advice is Usable | Green | Structured recommendations for medicines and healthtech rolled out, with first topics live Q1 25/26. Analytics providing insight on user behaviours where technology appraisals have been incorporated into guidelines to inform areas for improvement. The deliverables of the AWS proof of concept are on track, to inform options for healthcare recommendation content repurposing and our future approach to content creation, management and publication. | Agree next steps for delivery and implementation of a solution to meet the business needs for content creation, management and publication based upon recommendations and learnings from the AWS proof of concept
Demonstrable impact | Green | System intelligence and uptake measurement - Baseline established for measuring uptake in our priority areas. Maternity and neonatal insights pack published, insight pack on respiratory conditions in development. Implementation support - Formal partnership with CVD Prevent being explored to enhance uptake and adoption of cardiovascular disease guidance. Partnership manager now in post (joint role with Cancer Alliance) to focus on early value assessment for cancer. Tirzepatide and obesity guideline uptake being actively monitored. | Activity planning and scheduling to reflect the new uptake and adoption strategy, and an increase in demand for our support across NICE. Delay in NHSE commissioning guidance for tirzepatide implementation has caused delay in implementation and uncertainty for commissioners, providers and practitioners.
Brilliant organisation | Amber –forecast underspend​ exceeds target | People- First People Strategy event has kicked off (Weds 26th Feb). Employee Relations and Business Partnering Team- First session of Restorative Conversations has taken place across a broad range of colleagues. The recent Inclusion Pulse Survey (Dec 2024) shows an improvement in our performance on bullying and harassment, with 7% of staff saying they have experienced bullying and harassment in the past 12 months (an improvement from 10% last year) There have been improvements in the representation of ethnic minority, disabled and LGBTQ+ staff since Dec 2024 Indicative budgets for 25/26 issued by DHSC on 31 January. It included everything we’d proposed to be in our baseline including pressures (BNF, continuation of late-stage assessments). Receiving this confirmation at the early stage of business planning will be helpful for prioritisation decisions. The next phase of the corporate social responsibility commenced mid-February and is planned to conclude in May. Positive media engagement scores for recently published articles in digital channels. Individuals and teams are increasingly turning to the CQI method to tackle complex problems, with 60% of projects in the first round of business planning intending to use the method. | Forecast underspend exceeds our KPI. Capacity constraints and spend controls has meant that we have been unable to fully utilise the underspend arising from vacancies and increased income. There is uncertainty over the agreement of liabilities associated with the Manchester office move that could impact the year-end forecast outturn. Limited capacity to support teams applying CQI - Will be addressed through the ‘embedding improvement’ priority programme. Adapting to new ways of working within the People Team due to current changes for agility. Addressed through consistent, clear and open communication channels and need for colleagues to step up in respective spaces.
3

## Slide 4: Relevance: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
We are on track to present the refined HST criteria and thematic responses to stakeholder comments at the NICE Public Board Meeting on 19 March.
All Regulation 28 reports responded to within statutory timescales and delivery plan agreed at Patient Safety Oversight Group (PSOG) for the 25/26 patient safety priorities approved by the Board in December
We have incorporated Interventional Procedure topic selection reporting into the NICE Prioritisation Board to provide a more complete overview of the NICE work programme.
Key activities for next month
Publish the refined Highly Specialised Technologies criteria on 31 March 2025 (following sign off at the March NICE Board meeting).
Finalise the (interim) forward view for 2025-26 (to be published on 1 April).
Planning reflection and improvements session for Prioritisation Board (to be held on 2 April).
Progressing key internal actions required in response to patient safety issues raised by Regulation 28 reports and other sources, including Domestic Homicide Reviews
Key risks and mitigants
Risk | I | L | S | Key Controls
Some developer teams could reach their capacity and be unable to take new topics from Prioritisation Board (PB). | 3 | 4 | 15 | Developing ways to explore relative priority of topics considered by the Prioritisation Board - looking at potentially using the voting scores to determine relative priority, but it may also be a matter of re-presenting prioritised topics to the Prioritisation Board and then asking them to undertake a relative prioritisation exercise.
The Prioritisation Board could reach its capacity to work through and consider the volume of topic suggestions put forward. | 3 | 3 | 9 | Refining implementation of stage 1 process to improve efficiency and sustainability as we learn more now the ‘suggest a topic’ function is in use. We have refined the process by embedding a review by Consultant Clinical Advisors before Prioritisation Board. They review the stage one briefings and the proposed prioritisation decision; PB then reviews those decisions.
Volume and complexity of clarification requests impacts on Surveillance team capacity. | 3 | 3 | 9 | Engaging with Medicines evaluation team colleagues to develop processes for effectively responding to clarification requests.
Very low
Low
Medium
High
Very high

## Slide 5: Relevance: High-level summary of performance
NICE Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
% of positive decisions made by the Prioritisation Board that align to key NHS and social care priorities, including those described in our annual Forward View | 81% | 90% | N/A – new measure | N/A – new measure from Oct 24
% of responses to Regulation 28 reports, Health Services Safety Investigation Body (HSSIB) safety recommendations and safety alerts within specified and/or statutory timeframes | 100% | 95% | 90-95% | 
NICE Bus Plan Milestones | Due Date | RAG
Common prioritisation framework published following public consultation and agreement with system partners | Q1 | C
NICE’s Prioritisation Board launched | Q1 | C
Prioritisation Board’s forward look published | Q1 | C
Single horizon scanning function operational, linking with external providers | Q2 | C
Agreed an approach for recognising guidance from other organisations in areas where NICE does not produce guidance | Q2 | C
Consulted on any identified changes to routing criteria for Highly Specialised Technology Appraisals | Q4 | G
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
1
2 positive decisions in February. Monthly data not reported due to small numbers.
1
2
Responded to 1 Regulation 28 report in February within timelines. We are working on response to a further report received in February, but the response is not due until April.
All figures as of 28 February 2025 unless otherwise stated
2

## Slide 6: Timely & High-Quality: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Timeliness:
All guidance producing teams are now using MS Project to manage their timelines (with the majority of topics migrated). The enabling teams will migrate during Q4
Each service team are finishing their PDSA cycles in phase 1 and are agreeing priorities for phase 2
Held a Programme Retro to capture actions and lessons learnt for new services scheduled for 25/26
Methods
The consultation on health inequalities modular update received 130 comments from 26 respondents. Positive feedback on stakeholder engagement approach and content, some questions on implementation. Consultation response drafted
NICE Listens tender has closed. DHSC/NIHR R&D request for a large scale societal preference study relating to valuing severity has moved to stage 2
The Modular update Selection and Oversight Panel prioritised EQ-5D-5L adoption and surrogate endpoints for modular updates. Prioritised carer quality of life for work by DSU to prepare for modular update in 26/27
HealthTech manual consultation closes early March
Incorporation of TAs:
Remain on track to deliver over 170 Technology Appraisal incorporations by Q4
Significant stakeholder engagement with ABPI, DHSC/NHSE & Board
Rules Based Pathways
Meeting held with devolved nations to identify areas of collaboration
NIHR and OLS have joined NHSE/NICE programme board
Supported DHSC to draft the policy proposal for the NHS 10 Year Plan process
Key activities for next month
Timeliness:
Programme level process mapping and Time & Motion data collection Q4 to baseline ‘as is’
New Guidance Production Service(s) to launch and a workshop held in Manchester 25.03.25
Methods:
Make revisions to the health inequalities modular update wording and plan for implementation
Award NICE Listens contract to successful contractor.
Board seminar in March where Office of Health Economics (OHE) societal preference work will be discussed
Review feedback from HealthTech manual consultation
Incorporation of TAs
Further engagements with Board in Feb/March. Support for DHSC/NHSE Ministerial briefings.
Finalising plans and papers for stakeholder panels to begin to meet from April 2025
Review initial quantitative metrics for 9 incorporated guidelines
Rules Based Pathways
Develop NICE/NHSE programme plan
Mapping pathway into other activities to ensure clarify routes of access for tech categories and scenarios e.g. value-based procurement
Determine mechanisms to transact lifecycle guidance into NHS
Finalise mapping of commercial/adoption gateways with guidance
Key risks and mitigants
Workstream | Risk | I | L | S | Key Controls
Improving timeliness | Some teams may constrain their thinking and change idea opportunity identification, which may lead to a lack of significant improvement without digital transformation. | 4 | 4 | 16 | Review of the Planning Tools business continuity to help alleviate worries and shift the focus from new digital solutions.
 | The Medicines Evaluation Management of Change (MoC) presents an immediate risk to staff morale and engagement in Timeliness programme activities and a potential risk on the efficacy of change ideas tested in Medicines Evaluation | 3 | 4 | 12 | Work with each service to determine resource requirements in the teams and suggest any changes necessary to keep them operating effectively
 | Additive guidance production processes created through business planning meaning if there is a ‘do nothing’ approach, it will take longer and improvements made may have little to no impact on overall production timeline | 4 | 4 | 16 | Baseline time & motion for each stage of guidance producing processes in Feb/March and use information to estimate the impact of additive processes. This data set can then be used in Board making decisions
Methods | NICE’s decision around the severity modifier is not understood and is continually challenged by stakeholders | 3 | 4 | 12 | Continual monitoring of the use of the severity modifier. Engagement on industry-funded societal preference work. Launch NICE Listens severity weighting project
Very low
Low
Medium
High
Very high
6

## Slide 7: Timely & High-Quality: High-level summary of performance (1 of 2)
NICE Board KPIs (this slide are all NICE Board level KPIs ) | Actual YTD (Mean) | KPI performance target 24-25 | KPI starting performance 23-24 | % improvement / decrease vs 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal and divergent) | 339 days (N=49) | Improvement on 23-24 baseline | 452 days | 25% Improvement
Medicines - Median time between marketing authorisation and NICE recommendation (optimal and divergent) | 336 days (N=49) | Improvement on 23-24 baseline | 322 days | 4% Slower
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal) | 48 days (N=11) | 90 days | 36 days | Within target, but 33% above 23/24 mean
Medicines - Median time between marketing authorisation and NICE recommendation (optimal) | 44 days (N=11) | 90 days | 43 days | Within target, but 2% above 23/24 mean
Notes on RAG status:
DHSC and EEPRU to discuss scope of NIHR-funded project to examine interaction between health inequalities and severity. Drafted text on methods research priorities for publication on the website
Approval received for further recruitment to start, one part-time 8a in post & delivery of approved projects progressing as planned
NICE Board Milestones | Date | RAG
Start routinely incorporating relevant medicine technology appraisals in guidelines | Q1 | C
Understood baseline and opportunities for improvement in guidance producing processes | Q2 | C
Rolled out digital tools that support planning and identified future planning/scheduling needs | Q3 | C
Aligned and digitised some key steps in guidance producing processes | Q4 | C
Reviewed the use of the severity modifier in medicines evaluation and identified remedial actions if needed | Q2 | C
Updated methods for assessing health inequalities in guidance production | Q4 | G
Expanded HTA Lab capacity in line with new VPAG funding and delivered insightful outputs supporting high quality guidance | Q4 | G
Launched 8 Late-Stage Assessment topics | Q4 | C
Consulted (with NHSE) on a medtech rules-based pathway | Q1 | C
RAG rating key: C= complete; G= green; A= amber; R= red
1
1
All figures as of 28 February 2025 unless otherwise stated
2
2

## Slide 8: Timely & High-Quality: High-level summary of performance (2 of 2)
NICE Board KPIs (this slide are all NICE Board level KPIs ) | Actual YTD (Mean) | KPI performance target 24-25 | KPI starting performance 23-24 | % improvement / decrease vs 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (divergent) | 424 days (N=38) | Improvement on baseline 23-24 | 540 days | 21% improvement
Medicines - Median time between marketing authorisation and NICE recommendation (divergent) | 419 days (N=38) | Improvement on baseline 23-24 | 365 days | 15% slower
Medicines - Percentage of optimal topics published in 2024/25 (year to date) | 22% | Improvement on 23-24 baseline | 17.5% | 4.5% point improvement
HealthTech - Mean time to publish HealthTech guidance | 430 days (N=60) | Improvement on 23-24 baseline | 490 days | 12% improvement
HealthTech - Median time to publish HealthTech guidance | 399 days (N=3) | Improvement on 23-24 baseline | 402 Days | 1% improvement
CfG – % of quality standard updates published alongside guideline updates | 100% (N = 7) | 30% | N/A | N/A
% of TAs retrospectively incorporated by end of 24/25 | 66% (N=113) | 33% (170 out of 517) | N/A | N/A
KPIs reflect Q1 figures; Two KPIs have not been included here:
1) “Mean and median time to produce new guideline and guideline update” - data is being captured to establish a baseline for future measurement in 25-26;
2) “New NICE guidance within topic suites published within 6 months of Prioritisation Board's decision to update” - baseline data will start to be collected from August, and will be captured on a quarterly basis
All figures as of 28 February 2025 unless otherwise stated

## Slide 9: Usable: Exception report
RAG rating:
Content: Work to co-design and agree structured recommendations for guidelines is now underway. CHTE Recommendations- moved into the implementation phase and actively monitoring arising issues as new technology appraisals are being generated. The first topics go live Q1 2025/26 and will include a user behaviour dashboard to gain feedback.
Product: Captured and analysed performance information for Technology Appraisals that have been incorporated into Guidelines to date, to inform how many users are interacting with TAs in Guidelines, the behavioural steps they are going through to inform improvements for presentation and flow. Established analytics and Hotjar on current Search functions to set a performance baseline for 25/26 plans for improving search functionality. Head of Product appointed.
Knowledge Platform: The deliverables of the AWS proof of concept are on track for April, to inform options for healthcare recommendation content repurposing and our future approach to content management. Weekly meetings review data modelling, relationship mapping and ontologies and iterations, to deliver a workable semantic data model for scaling. These recommendations and output will inform next steps for meeting the business needs for content creation, management and publication.
Corporate website: while significant progress has been made in migrating corporate content to a new website, this will now continue and be complete by Q1 2025/26.
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Key activities for next month
Content: Continue work to co-design and agree structured recommendations for guidelines, together with working to improve how we digitally enable publication of guidance using new wording in existing publication systems. Define the scope of 2025/26 work to transform the way we create content. This will be a workstream of NICE’s Timeliness Programme.
Product: Work with publishing and TA incorporation working group to share findings from user behaviour to inform further user research/areas for improvement. Plan for user testing of structured recommendations in practice to inform broader content creation work.
Knowledge Platform: The initial working prototype of the semantic data model tested with the business to ensure the content is accurate to inform the recommendations for scale up of the data model. Continue weekly meetings between NICE and AWS to iterate and build semantic data model. Reconfirm business requirements for a solution to enable content creation, management and publication to triangulate with the recommendations and deliverables from the proof of concept and inform business decisions on next steps.
Corporate website: Continue work to develop and test new functionality within corporate website. Migrate final content by end of Q1 25/26
Key risks and mitigants
Amber
Very low
Low
Medium
High
Very high
Workstream | Risk | I | L | S | Key Controls
Structured Recommendations | If CfG colleagues at all levels are not convinced there is a need for change, then we will be unable to deliver Structured Recommendations and their benefits to our users | 4 | 4 | 16 | Continue to engage with colleagues to ensure they understand and are bought into the direction and benefits to our users that this work will bring; co-design solutions where possible

## Slide 10: Usable: High-level summary of performance
Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | % Increase vs 23-24
No of users accessing NICE website for guidance and advice | 17.1 million (24/25 Year to Date) | Increase on equivalent calendar months from 23-24 | 16.6 million (23/24 Year to end February) | +3%
 | As above | Increase on 23-24 | 18.3million (Full year) | N/A
Clicks on guidance products from the NICE corporate website (monthly figures) | 68,300 (24/25 Year to Date) | 86,500 (15% increase from equivalent months in 23-24) | 75,200 (23/24 Year to end February ) | -9%
 | As above | 95,700 (15% increase in full year) | 83,200 (Full year) | N/A
Bus Plan Milestones | Due Date | RAG
Complete migration to new corporate website | 30 Dec 24 | R
Complete proof of concepts with semantic data model to inform next steps of knowledge platform | 1 July 24 (expected Q4) | A
Agree standardised wording and structure for recommendations | 31 Dec 24 | C
Launch a new content governance process for CHTE and CfG | 31 Dec 24 | A
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
Removing old content has had an impact on clicks through to guidance. Any old articles that are driving a lot of traffic have been retained. Planned improvements to the SEO of the site will make it easier to search for guidance both on our website and from Google. Time period and newsworthiness of content is also a factor - spikes in traffic through to guidance come from high-profile news stories.
The first target of going live with the new homepage was met, with a plan to finish migration of the corporate pages by Q3 24/25. That timeline slipped but we are on track to complete end of Q1 25/26.
The revised start date agreed with Amazon Web Services was mid-October for a period of 12 weeks, so the delivery milestone was amended accordingly. Full reporting by April on track
Work on Content Governance has been absorbed into roll out of agreed structured recommendations and content creation transformation element of Timeliness Programme in 25/26.
1
3
2
1
2
3
4
4
All figures as of 28 February 2025 unless otherwise stated

## Slide 11: Impactful: Exception report
RAG rating:
Green
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
Uptake Measurement and System Intelligence​
We have completed the preparatory work and data definitions for the measurement of improvement in uptake of NICE guidance uptake in priority areas. We have completed the maternity and neonatal insights pack and a review of obesity medicines uptake. We have begun system intelligence and uptake analysis on respiratory conditions. We are bringing together learning from the year to develop a set of principles that guide our approach to system intelligence including how we collect, report and store data to improve impact.
Implementation support​
Draft strategy to improve the uptake and adoption of NICE guidance to go to Board in March
Dashboard produced to show traffic and usage stats for published obesity/tirzepatide resources and antenatal toolkit.​
Survey produced in conjunction with audience insights to seek feedback regarding maternity toolkit, to inform the revised version​
First two of five agreed products to support adoption and uptake of guidance delivered (Implementation chapter for Maternity and baseline assessment tool for Obesity).
Public Involvement best practice approach
Three continuous improvement projects scoped​: Experience of people and communities partners in committees and appraisals; Value and impact of involvement in NICE process; Involvement of carers.
Key activities for next month
Uptake measurement and System Intelligence​
We will progress insight work on our next two priority themes – respiratory and CVD.​
We will finalise the technical requirements for the measurement of improvement in uptake of NICE guidance uptake in priority areas.
​Implementation support
Final uptake and adoption strategy to be signed off by Board March 2025.
Implementation science training session taking place, open to all NICE staff.
Further obesity and tirzepatide implementation support in development
Stakeholder engagement planned to test out uptake and adoption priorities for 2025/26.
Public Involvement best practice approach
Process mapping for involvement for guidelines, medicines and health tech, as part of the timeliness programme, to improve flexible working and resourcing for involvement and engagement across all areas.
Key issues, risks and mitigants
Workstream | Risk | I | L | S | Key Controls
Implementation support | As a result of the launch of the Tirzepatide guidance in the current operating environment we may create significant implementation challenges for the system resulting in reputational damage | 3 | 3 | 9 | Implementation plan agreed Funding variation agreed
Very low
Low
Medium
High
Very high

## Slide 12: Impactful: High-level summary of performance
Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
Proportion of agreed priority guidance measures showing an improvement in national uptake (health and care system priority areas, populations with identified health inequalities, areas that matter most to people and the communities). | N/A | N/A | N/A Baseline to be established during 24/25 | N/A
All agreed priority areas have targeted implementation support package in place | 3 | 5 | 0 | 
New partnerships (including VCS organisations) to amplify the impact of NICE guidance in agreed priority areas. | 5 | 5 | 0 | 
Bus Plan Milestones | Due Date | RAG
Developed and implemented a fairer payment policy for involvement and engagement activity | 21 June 24 | C
Routine reporting of prioritised uptake measures in place | 31 July 24 | C
Joint plans in place to amplify the impact of NICE guidance through priority partnerships | 30 Sept 24 (moved from July 24 on 11/7/24) | C
5 implementation support packages initiated to address agreed priority areas | 30 Sep 24 | C
Programme of shared learning in place, connecting practitioners and commissioners to implementation best practice | 30 Nov 24 | A
Developed and tested impactful approaches for involving people and communities in developments in all new prioritised guidance | 31 Mar 25 | G
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
Baseline being established for 24/25 which will be available end of March 2025.
We approved a reduction in the number of implementation support packages to be delivered in 24/25 from 5 to 3, to ensure high quality resources are delivered with the capacity available.
Status is amber pending board approval of amended due date. The impactful oversight group agreed to extend the date to refresh the overall approach to shared learning to March 2025 and focus on delivering 10 case studies, evolving into the system engagement priority for 2025/26. The Board is requested to endorse the group’s decision to amend the due date to 31 Mar 25.
1
1
2
2
2
3
3
All figures as of 28 February 2025 unless otherwise stated

## Slide 13: Brilliant Organisation: Exception report
RAG rating:
Amber
DIT​
Preferred supplier arrangements for contingent labour and approvals for the ongoing extension to use of infrastructure contractors progressing with Finance, Corporate and Commercial team (FCC).
Business Impact assessment to identify and evaluate the effects on disruptions on business functions and processes commenced. This will lead to more detailed business continuity/disaster recovery for our key systems across IT and the business and is part of our ongoing cyber strategy to inform mitigation and response plans.
Business Planning discussions taken place with Executive Team taken place to confirm prioritised approach to delivery 25/26
Comms
The healthtech transformation carousel on LinkedIn was the best performing piece of content on social in Feb with 22.5k impressions, 5.3k engagements and a 25.5% engagement rate (benchmark is 5%).
Carried out a user survey to learn more about our audience on Whatsapp. Positive findings with 62% of users identifying as healthcare professionals. 100% of users say they will continue to use the channel and vast majority happy with the content provided.
Parliamentary engagement event was delivered successfully with opening remarks from NICE Minister Karin Smyth. 80 stakeholders in attendance, including ~25 MPs and Peers.
Delivered a series of face-to-face meetings between the CEO & influential parliamentarians including Health select committee members.
Finance
The Finance and RIA teams have been awarded Level 2 re-accreditation under the Towards
Excellence Scheme by the NHS Finance Leadership Council.
Indicative budget for 25/26 was confirmed by DHSC on 31 January and our baseline proposals were successful, ensuring we start the next financial sure on a sure footing financially.
People
Values work: Over the course of the year 74% of colleagues have told us through our activities that they have a clear understanding of our values and what it means to live them. Project Nova: 3 workstreams transitioning into BAU. Work has started building a People Strategy. ER: First Restorative Conversations training session delivered to 30 colleagues to support cultural messaging for RJLC. OD: Bullying and Harassment findings have been circulated to the Board following inquiry work. Our latest data (December 2024) shows that there has been an improvement in overall levels of reports of these behaviours over the past year. It also shows that levels of confidence in NICE taking ‘effective action’ against bullying and harassment continue to rise.
Key activities for next month
DIT​​
Finalisation of directorate business plan and input to wider business planning
Ongoing work with consultancy to review applications technical debt
Completion of move to GovWIFI for Manchester Office
Comms
NICE Conference for external stakeholders takes place in Manchester on 27 March. Nearly 500 delegates have registered (target: 400). The event will feature 35 speakers from the health and care system, third sector, industry and NICE. 10 organisations will be exhibiting at, or sponsoring, the event (including NIHR, NHS Blood and Transplant and BioMerieux).
Internal comms activity to support business planning continues with roadshows in March and "learn a bit about" sessions through Spring.
Finance
Month 9 interim audit is taking place ahead of year-end.
Responding to DHSC's Zero Based Review and Spending Review Phase 2 2026-29 commissions and supporting business planning.
People
Business Partnering workshops commencing, identification of success measures and alignment of central function approach following Organisational Development Action Research methodology.
Continuation of creating NICE's first dedicated People Strategy, to address strategic problems and ensure alignment with NHS 10-year plan and NICE's strategic ambitions.
Staff and Pulse surveys being redesigned to ensure alignment with organisational priorities.
CQI
Embedding improvement into our ways of working has been adopted as a strategic priority for the next financial year. Work will start next month to procure a strategic provider, establish workstreams and wraparound support for teams undertaking CQI projects.
Key issues, risks and mitigants
Very low
Low
Medium
High
Very high
Workstream | Risk | I | L | S | Key Controls
DIT | Cyber security (as per strategic risks) | 5 | 4 | 20 | Cyber activities are being progressed and reported to Audit and Risk Assurance Committee. Risk is being tracked in the Strategic Risk Register. Risk updated to reflect impact of AI
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs

## Slide 14: Brilliant organisation: High-level summary of performance
NICE Business plan KPIs | Actual YTD | KPI Performance target 24-25 | KPI starting Performance 23-24 | % Increase vs 23-24
Media coverage of NICE that is positive in sentiment | 79%* | 80% | 80% | 1-percentage points (pp)
Media coverage that is generated by NICE includes at least one NICE key message | 54%* | 60% | 54% | 0+ pp
Representation of ethnic minority, disabled and LGBTQ+ colleagues at all levels | Ethnic 20.70% Disabled 11% LGBTQ+ 8.90% | Ethnic 20.3% Disabled 10.44% LGBTQ+ 9.17% | Ethnic 18.21​% Disabled​ 9.49% LGBTQ+​ 8.34% | +2.49pp +1.51pp +0.56pp
Number of informal resolutions | 57 | 32 (50% increase) | 21 | +171%
Financial position (current forecast assumption) | Full-year forecast outturn £1.8m underspend* | No deficit, Surplus <£1m | No deficit, Surplus <£1m (Achieved) | 
NICE Bus Plan Milestones | Due Date | RAG
Launched a new Equality, Diversity and Inclusion Roadmap including new objectives to improve staff experience and representation | Q1 | C
Rolled out Power-BI enabled detailed financial forecasting and scenario planning to increase accuracy of forecasts and engage operational teams | Q3 | C
Fully embedded finance business partnering to improve financial input into directorate decisions | Q4 | G
Completed a successful office move to our new Manchester office | Q3 | C
Notes on RAG status:
This KPI is volatile and is dependent on how much of our spokespeople's quotes the media choose to use.
Although slightly below target, gradual improvements are being made against the 23/24 starting performance.
The KPI is amber due to a strong performance for TA/HST cost recovery and a higher than planned vacancy rate, meaning NICE is forecast to underspend by £2.3m against plan.
1
RAG rating key: C= complete; G= green; A= amber; R= red
1
2
2
3
3
All figures as of 28 February 2025 unless otherwise stated
*figure correct as of 31 January 2025

## Slide 15: Financial performance as at 31 January 2025
Spend category​ | YTD ​ budget​ £000​ | YTD​ actual £000​ | YTD Variance​ £000​ | Annual budget £000​ | Estimated outturn £000​ | Forecast variance £000​ | Commentary​
Pay​ | 51,714 | 50,183 | (1,531) | 61,875 | 60,502 | (1,373) | Pay underspend (3.3% against budget) driven by vacancies.​
Non-Pay​ | 19,812 | 19,712 | (100) | 25,046 | 25,857 | 811 | In year-spend is on plan, forecast overspend is driven by office move liabilities.​
Income​ | (22,534) | (23,409) | (875) | (27,040) | (28,233) | (1,193) | Forecast surplus income is due to TA/HST cost recovery being above plan.​
Total​* | 48,991 | 46,486 | (2,505) | 59,881 | 58,126 | (1,755) | ​Current forecast underspend, subject to change (see table below).
*Note: The YTD budget and Annual budget figures for January have been manually adjusted to reflect the confirmation in February that the OLS funding will not be transferred.
The above financial statement shows our performance against our Non-Ringfenced Revenue budget, which is agreed annually with the DHSC.
Foreword look and budget update
Forecast uncertainty:
There remains uncertainty in costs and liabilities associated with the office. Firstly, negotiations around dilapidation costs of the City Tower lease are not settled and could still change from the current estimate. Secondly, the new Manchester office lease is expected to be treated as a right of use asset to be depreciated under IFRS 16 rules. This is assumed in the forecast, however until the lease is signed some costs may be treated as a short-term operating lease and treated as a revenue cost not shown in the estimated outturn above.​
If either / both of these scenarios materialise, the forecast underspend will likely decrease from the value shown above.
Spending review
We have received confirmation of our 2025/26 budget following phase 1 of the Spending Review. The amount was as expected, including adding recurrent funding to our baseline to continue developing Late- Stage Assessments and budget cover for the inflationary pressure of the 24/25 NHS pay award.
Phase 2 of the Spending review (covering the period 2026-29) is currently in progress alongside development of the 10-year plan.
Update since last Board meeting
At December’s board meeting, the financial position was reported as at the end of October 24. Since then, the forecast underspend has increased from £1.4m to £1.8m (£0.4m increase).​ There have been several movements to account for this net change:
An expected budget transfer for OLS activity will not happen due to the underspend (£1.1m reduction in budget).
The forecast assumption liabilities and costs associated with the office move has reduced from £2m to £1m (although uncertainty remains).
Costs for planned DIT activity were lower than expected and some costs associated with addressing tech debt were delayed due the office move and capacity constraints.
A summary of the changes since the last IPR is shown in the table below.
Comparison (£m) | Oct 24 | Jan 25 | Movement | Change
Annual Budget | 61.0 | 59.9 | 1.1 | Reduced OLS Funding
Forecast outturn | 59.6 | 58.1 | -1.5 | Reduced office move costs (£1.0m), reduced digital spend (£0.5m)
Forecast variance | -1.4 | -1.8 | -0.4 | £0.4m net increase in forecast underspend

## Slide 16: Appendix to Brilliant organisation
 | YTD | Target | RAG
Sickness rate - overall | 2.75% | 3% | A
Total turnover rate | 11.44% | N/A | N/A
Voluntary turnover | 7.36% | N/A | N/A
Non voluntary turnover | 4.08% | N/A | N/A
Complaints | 100% of complaints responded to within 20 working days | 80% of complaints acknowledged and responded to within 20 working days | G
People
Communications
 | YTD | Target | RAG
FOIs | 98% | 90% of FOIs responded to with 20 working days | G
Parliamentary questions | 98% | 90% of Parliamentary Questions responded to within the requested time frame | G
Newsletter subscribers | 66,340 | 69,771 (this target represents a 10% increase on last year's subscriber total) | A
Social media followers – new WhatsApp channel | 8,186k (launched 22/07) | 5k followers on Whatsapp since 22 July surpassing our KPI of 2k after 6 months | G
RAG rating key: C= complete; G= green; A= amber; R= Red
All figures as of 28 February 2025 unless otherwise stated

## Slide 17: DDAT Live Services
Stability
Commentary:
Microsoft Cyber Security assessment completed with NICE scoring higher than average at initial assessment showing a good level of maturity and best practice
NICE responses to NHS critical cyber alerting are consistently resulting in deployed fixes within 24 hours of notification, well within the expected timescale of 14 days.
3 x cyber incidents investigated during Feb 2025 - all 3 resulted from detection of malware/adware on end user devices. Resolved.
Manchester office Wi-Fi and GovWi-Fi progressing
Annual penetration testing of cloud and on-premise infrastructure and NICE externally facing live services underway
3 cyber incidents across Dec/Jan. One foiled due to protections in place. Two related to staff use or loss of laptop. No compromises to NICE identified
Lower than predicted compromise rate to recent phishing campaign across NICE.
NCSC SIRO Training held in Feb for key NICE roles.
NICE achieved certification against Cyber Essentials (certificate awarded 24th December 2024)
Data as at 28 Feb

## Slide 18: Headline description of key projects to deliver NICE aims
NICE aim | Project name | Project headline description
Timely and High-Quality Guidance | Rules Based Pathway (RBP) | Establishing the rules and principles on which NICE and NHS England will work in partnership to evaluate, commission and fund medical technologies
 | Improving Timeliness and Staff experience (ITSE) | Improved timeliness by standardising and improving processes across guidance producing centres, through the use of digital tools and continuous improvement approaches
 | Incorporation of TAs into guidelines | Inclusion of medicines and HealthTech recommendations within guidelines to make NICE guidance more useful and useable
Usable | Content governance and structured recommendations | Organisations that produce digital content need a process to ensure their content is produced efficiently, and is consistent, of high-quality and accurate. This is content governance. We will create a governance framework that outlines how committee recommendations are converted into guidance products that are centred around user needs and agreed house style. Create more actionable, structured recommendations across different types of guidance to benefit users.
 | Knowledge platform | Procure and implement knowledge platform which structured content will be migrated to.
Impactful | Measurement uptake | Measure uptake of our guidance and use that data to ensure NICE focuses on our priorities.
 | Amplify priority partnerships | Work closely with critical stakeholders who can amplify our guidance in priority areas to help get the best care to patients fast.
 | Targeted implementation support | We will use implementation science to focus on system priorities populations with identified health in equalities and other areas that matter most to people and communities.
 | Public involvement best practice approach | Implementing a new way to reach the right members of the public at the right time in the right way to increase uptake of guidance and support getting the best care to people fast.
 | Implementation support toolkits | Development of comprehensive implementation support toolkits where implementation challenges already exist or are anticipated