## Slide 1: Integrated Performance Report (IPR)
Sep 2024

## Slide 2: Sep 2024 IPR contents page
Section | Slide / chart number | Lead
Executive summary – highlights and escalation points | 3 | All ET
Summary of performance – Relevance | 4-5 | Jonathan Benger
Summary of performance – Timely and high quality | 6-8 | Sam Roberts
Summary of performance – Useable | 9-10 | Clare Morgan
Summary of performance – Demonstrable Impact | 11-12 | Clare Morgan
Summary of performance – Organisational Brilliance | 13-15 | Helen Brown
Finance | 16 | Pete Thomas

## Slide 3: Executive summary on NICE Business Plan progress 2024-25 (Sep 2024)
Area | Current Status | Key highlights and successes | Key challenges
Focusing on What is Most Relevant | Green | Key areas for Prioritisation Board improvement have been identified, and plans have been made to deliver those improvements. Achieved 95% of responses to arising patient safety signals, to target within required timeframes (Annual report to Board December 2024). | The volume of topic suggestions for Prioritisation Board and capacity to work them through. This is being mitigated by a new process for screening topics. Developer teams reaching capacity to take new topics from Prioritisation Board. This is being mitigated by developing ways to explore relative priority of topics considered by Prioritisation Board.
Providing High Quality & Timely Advice | Amber –significant resource demand for Improving Timeliness programme | Timeliness is improving across the board relative to last year (though sample sizes are small). Improving timeliness of guidance production and staff experience: Continuous quality improvement approach outlined and approved. External Continuous Quality Improvement delivery partner appointed (IHI). NICE/NHSE MedTech Rules-Based Pathway (RBP): Consultation closed with over 200 responses. Analysis of those responses and detailed design of the pathway is progressing well. Incorporation of technology appraisals (TAs) into guidelines: Batch two of a further 33 TAs have been signed off at Programme Board and are due to publish later this month. Process and Principles for incorporation have been agreed, including the process for clinical input. | Improving timeliness programme requires a very significant time commitment from service owners and ET leads, and we have not yet tested whether it is manageable. Implementation of MS Project (to replace current timeline management approaches) will now be completed for all guidance producing teams by end-December 2024, not mid-October 2024, due to staff capacity issues and external partner availability. Plans for prospective incorporation are underway but were delayed from Q1 due to issues with publishing the identified TAs
Ensuring our Advice is Useable | Amber – uncertainty due to new strategy development | Website visits continue to outstrip 23/24 performance. Draft of useable product strategy produced, addressing the barriers (24/25) and the long term aim to make guidance products more useable for practitioners, commissioners and providers. Further engagement with colleagues and Board scheduled. Content governance: roles/responsibilities and decision-making framework drafted for discussion/approval. Structured recommendations: core components of guidelines recommendations devised and agreed, with further detailed discussions on specific aspects to follow. | Uncertainty remains over the programme until the new strategy is finalised. Capacity of the guidance teams to engage with the content governance and structured recommendations work. This is mitigated by minimising the time requirement for meetings and involving the teams only when necessary/appropriate. Timelines for work on structured recommendations will potentially be impacted by AWS activity, as the same staff will need to be involved. This is being actively mitigated by forward capacity planning.
Demonstrable impact | Green | Collaboration agreements in development with our priority implementation partnerships. Process established for sharing routine system intelligence and uptake measurement data into NICE core decision making, to increase overall focus on implementation and impact. Composite video patient stories (Tourettes Syndrome and Tics) used for the first time to inform Committee discussion and decision making. | Stakeholder feedback suggests significant implementation risks associated with Tirzepatide TA and obesity management guidance. This is being mitigated by the development of an extensive package of implementation support, which is being developed with stakeholder input, including clinicians and commissioners.
Brilliant organisation | Amber –significant under-spend​ and office move challenges | Making good progress against targets for positive media coverage and staff diversity. Coverage of Enhertu and Lecanemab final guidance was balanced and accurate despite the obvious disappointment of key groups | Significant YTD underspend of £1.9m driven by higher than anticipated vacancy rates, reserves not being drawn down and higher income from TA-HST. This is down from £2.2m last month. Ongoing challenges with the office move due to staff absences. Risk that the technology may not be ready to use on first day of relocation.

## Slide 4: Relevance: Exception report
Key activities for next month
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
RAG rating:
Green
Initial workplan for continuous improvement of Prioritisation Board developed, which will consider opportunities for improvement across areas such as how we communicate decisions and how we involve patients.
Revised process implemented for efficient processing of Stage 1* briefings for new topics suggested through the ‘single front door’.
On patient safety, we have continued to achieve our target (95%) of responses to Regulation 28 reports**, Health Services Safety Investigation Body (HSSIB) safety recommendations and safety alerts within specified and/or statutory timeframes
* The screening/shortlisting stage
** Report to an individual, organisations, local authorities or government departments and their agencies where a coroner believes that action should be taken to prevent further deaths
Workplan for continuous improvement of the Prioritisation Board to be reviewed and agreed by the Board
We are inputting to the responses to three further Regulation 28 reports from HM Coroner due within the next month
Key risks and mitigants
Risk | I | L | S | Key Controls
Developer teams reaching capacity to take new topics from Prioritisation Board | 3 | 4 | 12 | Developing ways to explore relative priority of topics considered by the Prioritisation Board
Volume of topic suggestions for Prioritisation Board and capacity to work them through | 3 | 3 | 9 | Refining implementation of stage 1 process to improve efficiency and sustainability as we learn more now the ‘suggest a topic’ function is in use
Insufficient capacity in either patient safety or enquiry handling team to achieve required response time target. | 3 | 2 | 6 | The teams have effective processes and lines of two-way communication for patient safety advice and input to develop the response. The process and team capacity is routinely reviewed to ensure it remains optimised to deliver effective and timely advice
Very low
Low
Medium
High
Very high

## Slide 5: Relevance: High-level summary of performance
NICE Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
% of positive decisions made by the Prioritisation Board that align to the key NHS and social care priorities described in our annual Forward View | N/A* data will start to be collected from Aug | 90% | N/A – new measure | N/A
% of responses to Regulation 28 reports, HSSIB safety recommendations and safety alerts within specified and/or statutory timeframes | 95% | 95% | 90-95% | 
NICE Bus Plan Milestones | Due Date | RAG
Common prioritisation framework published following public consultation and agreement with system partners | Q1 | C
NICE’s Prioritisation Board launched | Q1 | C
Prioritisation Board’s forward look published | Q1 | C
Single horizon scanning function operational, linking with external providers | Q2 | A
Agreed an approach for recognising guidance from other organisations in areas where NICE does not produce guidance | Q2 | G
Consulted on any identified changes to routing criteria for Highly Specialised Technology Appraisals | Q4 | G
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
1
1
Recruitment timelines for horizon scanning roles may mean not all have started by end of Sept
All figures as of 31 July 2024 unless otherwise stated

## Slide 6: Timely & High-Quality: Exception report
Key activities for next month
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
RAG rating:
Amber
Improving timeliness of guidance production and staff experience:
Business case approved by the NICE Board in July 2024
Programme Manager role currently in development
Service owners and ET leads agreed for 3 of 4 initial services
Committee members surveyed on current practice and process 'pain points'
Late Stage Assessment:
First topic (TAVI) went to committee in July
Incorporation of TAs into guidelines:
Plan Do Study Act (PDSA) cycle took place in July. Lessons learnt from initial work
Next batch of incorporated TAs ready for sign off prior to publication
Rules Based Pathway
Joint NICE/NHSE/DHSC Steering Group, Working Group, and Task and Finish Groups have been established and are operational
NICE is leading on topic selection and NICE assessment. NICE has drafted hypotheses for how these processes need to be adapted and is iterating with other interested parties
Improving Timeliness:
  Agree next steps for committee collaboration solution (following completion of exploration of digital tools)
  Recruitment for a Programme Director has commenced. Interviews expected in early October.
  Agree NICE wide approach to deliver Continuous Quality Improvement
  Start onboarding and problem identification phases of Continuous Quality Improvement cycles for the first four services (Topic Management, Committee Management, Stakeholder Management and Management Information)
  Incorporation of Technology Appraisals into guidelines:
  Further refinement of the process document to determine how to handle publication of managed access recommendations
  Rules Based Pathway
  Analyse all responses to the consultation and begin to prepare NICE/NHSE’s response
  Continue to build the pipeline of technologies that could receive a full NICE recommendation
  Methods
  Preparation of initial draft health inequalities plan for 2025-26 by end of Sep
Workstream | Risk | I | L | S | Key Controls
Improving Timeliness | Some tools that are due to be retired in March 2025 do not currently have an alternative solution | 3 | 4 | 12 | Exploring alternative approaches to accelerate development of stakeholder management solutions
 | Service owners and ET leads do not have capacity to drive forward the programme at the pace required | 4 | 4 | 16 | Meetings scheduled with ET leads to agree responsibilities and test capacity to fulfil them. Further controls may be put in place following this.
Incorporation | Publishing incorporated TAs may influence the public narrative and surface issues that would not otherwise be prevalent. | 3 | 3 | 9 | Understanding the wider impact that the publication batch may have, particularly in relation to topic and guideline area
Rules Based Pathway | The pipeline of technologies that could receive a full NICE recommendation is thin, which could lead to underspend against the expected budget available | 4 | 3 | 12 | Expand engagement to stakeholders that are more likely to be aware of high impact technologies with enough evidence to receive a full recommendation
Improving Timeliness:
First four Service Owners and ET relationship sponsor pairings confirmed
Communications hub created and published for NICE staff to learn more about the programme
Workshops exploring the potential use of AI (MS Co-Pilot) have been held.
Incorporation of Technology Appraisals into guidelines:
Second batch of an additional 33 incorporated Technology Appraisals have been signed off and are now ready for publication in early Sept
Rules Based Pathway
201 responses received to the consultation. Analysis of responses is underway
Detailed design of the NICE-led segments of the pathway (topic selection and NICE Assessment) is progressing well and being refined through the consultation feedback received
Methods
Review of all current NICE health inequalities activity completed, with workshop involving colleagues working in methods, implementation and people and communities
First phase of the assessment of the impact of moving from the End of Life weighting to the Severity Modifier is complete, and is due to be discussed with the Board.
Key risks and mitigants
Very low
Low
Medium
High
Very high

## Slide 7: Timely & High-Quality: High-level summary of performance (1 of 2)
Notes on RAG status:
Plans for prospective incorporation are underway. This was delayed from Q1 due to issues with publishing the identified TAs
NICE Board KPIs (this slide are all NICE Board level KPIs ) | Actual YTD (Mean) | KPI performance target 24-25 | KPI starting performance 23-24 | % improvement / decrease vs 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal and divergent) | 349 days (N=12) | Improvement on 23-24 baseline | 452 days | 23% Improvement
Medicines - Median time between marketing authorisation and NICE recommendation (optimal and divergent) | 298 days (N=12) | Improvement on 23-24 baseline | 322 days | 8% Improvement
Medicines - Mean time between marketing authorisation and NICE recommendation (optimal) | 80 days (N=2) | 90 days | 36 days | Within target, but 121% above 23/24 mean NOTE: only two data points
Medicines - Median time between marketing authorisation and NICE recommendation (optimal) | 80 days (N=2) | 90 days | 43 days | Within target, but 85% above 23/24 mean NOTE: only two data points
NICE Board Milestones | Date | RAG
Start routinely incorporating relevant medicine technology appraisals in guidelines | Q1 | A
Understood baseline and opportunities for improvement in guidance producing processes | Q2 | G
Rolled out digital tools that support planning and identified future planning/scheduling needs | Q3 | G
Aligned and digitised some key steps in guidance producing processes | Q4 | G
Reviewed the use of the severity modifier in medicines evaluation and identified remedial actions if needed | Q2 | G
Updated methods for assessing health inequalities in guidance production | Q4 | G
Expanded HTA Lab capacity in line with new VPAG funding and delivered insightful outputs supporting high quality guidance | Q4 | G
Launched 8 Late-Stage Assessment topics | Q4 | G
Consulted (with NHSE) on a medtech rules-based pathway | Q1 | C
RAG rating key: C= complete; G= green; A= amber; R= red
1
1
All figures as of 31 July 2024 unless otherwise stated

## Slide 8: Timely & High-Quality: High-level summary of performance (2 of 2)
NICE Board KPIs (this slide are all NICE Board level KPIs ) | Actual YTD (Mean) | KPI performance target 24-25 | KPI starting performance 23-24 | % improvement / decrease vs 23-24 performance
Medicines - Mean time between marketing authorisation and NICE recommendation (divergent) | 402 days (N=10) | Improvement on baseline 23-24 | 540 days | 26% improvement
Medicines - Median time between marketing authorisation and NICE recommendation (divergent) | 389 days (N=10) | Improvement on baseline 23-24 | 365 days | 7% reduction
Medicines - Improvement year on year in optimal topics as a % of all medicines’ appraisals | 16.7% (N=2) | Improvement on 23-24 baseline | 17.5% | -0.8% points
HealthTech - Mean time to publish HealthTech guidance | 386 days (N=14) | Improvement on 23-24 baseline | 490 days | 21% improvement
HealthTech - Median time to publish HealthTech guidance | 376 days (N=14) | Improvement on 23-24 baseline | 402 Days | 6% improvement
CfG – % of quality standard updates published alongside guideline updates | N/A | 30% | N/A | N/A
% of TAs retrospectively incorporated by end of 24/25 | 9% (N=47) | 33% (170 out of 517) | 0 | 47 achieved by end of July against target of 42 for Q1
KPIs reflect Q1 figures; Two KPIs have not been included here:
1) “Mean and median time to produce new guideline and guideline update” - data is being captured to establish a baseline for future measurement in 25-26;
2) “New NICE guidance within topic suites published within 6 months of Prioritisation Board's decision to update” - baseline data will start to be collected from August, and will be captured on a quarterly basis
Notes on RAG status:
Low sample sizes make it difficult to compare timeliness at this stage in the year to full-year averages
The KPI is projected to rise to 31% by the end of the year
1
2
1
All figures as of 31 July 2024 unless otherwise stated
2

## Slide 9: Useable: Exception report
Key activities for next month
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
RAG rating:
Amber
Draft of NICE useable product strategy produced (including how we address the barriers to progress -in 24/25 - and deliver the long term aim to make guidance products more useable for practitioners, commissioners and providers). This will go to a Board discussion in September
We have agreed changes to how guidelines will be written to improve how they are structured and be more explicit about recommended clinician actions.
We have agreed changes to all medicine and medtech appraisals that align wording and clarify recommended clinician and commissioner actions. We are awaiting legal feedback.
Content governance: consulting with guidance developers on draft framework for decision making about wording and presentation, and draft roles and responsibilities for developer and publishing teams
Discussions under way with AWS to finalise project scope.
Setting up a separate working group to focus on ‘strength of recommendations’ as part of our structured recommendation frameworks project.
Finalising scope and beginning agile sprints with Amazon Web Services.
Content governance: agree decision-making framework and implement in Medicines and Health Tech.
Discussions with Centre for Guidelines about building content governance and content design principles into new guideline development and improving existing content.
Agree useable product strategy at Board and begin the theory of change review to develop a 2-year implementation plan.
Risk | I | L | S | Key Controls
Work packages to create a structured recommendations framework, content governance and the foundational work to develop a digital knowledge platform have been developed independently. Unless mitigated collectively there is a risk that our foundational work does not enable NICE to create innovative guidance products. | 3 | 3 | 9 | Programme management of the useable programme actively manages all foundational aspects, accountability, risk management, resource allocation and independencies to meet 24/25 objectives. Refreshed delivery plan and outcomes incorporated into Board proposal.
The long-term aim, ambitions and measures of success for the USEABLE programme are unclear, which means we deliver siloed work which does not improve the Useability of our guidance, in the areas prioritised by our users. | 4 | 2 | 8 | Create consensus on the long, mid and short term aims for the USEABLE programme, defining the context, drivers for change, deliverables and measures of success (useable product strategy) to underpin a 2-3 year programme of work. Approach to be agreed by the Board in Sept 24
Key risks and mitigants
Very low
Low
Medium
High
Very high

## Slide 10: Useable: High-level summary of performance
Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | % Increase vs 23-24
No of users accessing NICE website for guidance and advice | 6.2 million (24/25 Year to Date) | Increase on equivalent calendar months from 23-24 | 6 million (23/24 Year to end-July) | +3%
 | As above | Increase on 23-24 | 18.278 million (Full year) | N/A
Clicks on guidance products from the NICE corporate website (monthly figures) | 24,600 (24/25 Year to Date) | 25.200 (15% increase from equivalent months in 23-24) | 27,700 (23/24 Year to end-July) | -11%
 | As above | 95,700 (15% increase in full year) | 83,200 (Full year) | N/A
Bus Plan Milestones | Due Date | RAG
Complete migration to new corporate website | 30 Sept 24 | G
Complete proof of concepts with semantic data model to inform next steps of knowledge platform | 1 July 24 (expected Q3) | A
Agree standardised wording and structure for recommendations | 31 Dec 24 | G
Launch a new content governance process | 31 Dec 24 | G
RAG rating key: C= complete; G= green; A= amber; R= red
Notes on RAG status:
This can be attributed to the pre-election period, where NICE communications and publications were restricted.
The intended commencement of the POC is mid-September to begin for a period of 12 weeks. The lead-in workshops are being put in place via Amazon Web Services, and the first one took place on 26 August.
1
1
2
2
All figures as of 31 July 2024 unless otherwise stated

## Slide 11: Impactful: Exception report
Key activities for next month
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
RAG rating:
Green
Measuring uptake
Processes for routine system intelligence and uptake measurement data to be inputted into key guideline decision making processes now agreed.
Quarterly Intelligence report produced and intelligence directed to relevant teams and functions in NICE.
Process to coordinate requests for data, intelligence and insight across different organisational functions agreed.
Deep dive on maternity and neonatal guidance uptake and system intelligence started.
Increasing uptake
Collaboration agreements in development with our priority partnerships, to support implementation and increased uptake.
Draft annual workplan agreed with Health Innovation Networks, focusing on CVD, obesity and weight management, and real world evidence collection for early value assessments
Improving engagement
Work in progress across our expert panel and VCSE forum and to establish NICE leaders to provide the infrastructure for the oversight group.
Measuring uptake
Extract maternity and neonatal data in prioritised areas, identifying variation and developing insights.
Working on coordinated response to data, intelligence and insight requests. Key examples include menopause request for prioritisation function and cancer request for guidelines programme.
Increasing uptake
Finalise collaboration agreements and joint work plans with all priority partnerships.
Further development of obesity implementation support
Improving engagement
Recruit non-executive director to support the People and Communities work programme and agree terms of reference for oversight board and start recruitment process.
Relaunch of VCSE forum event September.
Key issues, risks and mitigants
Workstream | Risk | I | L | S | Key Controls
Implementation support | Feedback from stakeholders has highlighted potential implementation risks with Tirzepatide TA | 4 | 3 | 12 | VPAG implementation toolkit being developed to address key implementation risks, with extensive user/stakeholder involvement.
Uptake measurement | There is a risk we raise expectations about increasing levels of all guidance uptake with the KPI about uptake measurement. | 3 | 3 | 9 | Careful communication about prioritised areas and develop roadmap for future expansion of uptake measurement.
Very low
Low
Medium
High
Very high

## Slide 12: Impactful: High-level summary of performance
Business plan KPIs | Actual YTD | KPI performance target 24-25 | KPI starting performance 23-24 | Trajectory
Proportion of agreed priority guidance measures showing an improvement in national uptake (health and care system priority areas, populations with identified health inequalities, areas that matter most to people and the communities). | N/A | N/A | N/A Baseline to be established during 24/25 | N/A
All agreed priority areas have targeted implementation support package in place | 0 *In line with expected milestones | 5 | 0 | 
New partnerships (including VCS organisations) to amplify the impact of NICE guidance in agreed priority areas. | 0 *as above | 5 | 0 | 
Bus Plan Milestones | Due Date | RAG
Developed and implemented a fairer payment policy for involvement and engagement activity | 21 June 24 | C
Routine reporting of prioritised uptake measures in place | 31 July 24 | C
Joint plans in place to amplify the impact of NICE guidance through priority partnerships | 30 Sept 24 (moved from July 24 on 11/7/24) | G
5 implementation support packages initiated to address agreed priority areas | 30 Sep 24 | G
Programme of shared learning in place, connecting practitioners and commissioners to implementation best practice | 30 Nov 24 | G
Developed and tested impactful approaches for involving people and communities in developments in all new prioritised guidance | 31 Mar 25 | G
RAG rating key: C= complete; G= green; A= amber; R= red
All figures as of 31 July 2024 unless otherwise stated

## Slide 13: Brilliant Organisation: Exception report
Key activities for next month
Key highlights / what’s been achieved and headline progress towards outcomes and KPIs
RAG rating:
Amber
Financial performance: The cost recovery performance of TA/HST has improved significantly due to improved throughput, with income being £0.7m above plan year to date and 96% of costs being recovered (compared to 79% in 2023/24).
People: The Equality, Diversity and Inclusion roadmap is now in place, which we expect promote a better experience for ethnic minority, disabled and LGBTQ+ colleagues at NICE, and boost representation.
Communications: We conducted a review of our internal communications channels and highlighted a number of improvements to further improve the effectiveness of our communications with staff to support our transformation.
Financial outlook: Engage with DHSC to support the Autumn Budget 2024 and Spending Review 2025 commissions, which will have direct impact on business plans and budgets in the current and future financial years.
People: First draft of a new Restorative and Just Policy to be completed, which we expect to drive increased use of informal resolutions once implemented.
People: Working with staff networks to help staff, and particularly line managers, to support colleagues affected by trauma and discrimination. This is part of NICE’s ongoing work following the recent riots and civil unrest.
Key issues, risks and mitigants
Risk | I | L | S | Key Controls
There has been a slight delay in confirming the exact format for the leadership development programme. | 3 | 3 | 9 | It's important all stakeholders are aligned, and the content is complementary to other key development work. This has now been resolved so design work can begin, but the programme may still be ongoing as we enter 25/26
There is a risk we miss our KPI target to end the year with a surplus of less than £1m. | 2 | 4 | 8 | The normal mitigations to utilise a surplus are to bring forward future planned activity or pump-prime new opportunities. However, the DHSC has instructed all ALB’s including NICE to hold back spend on uncommitted contracts, and enhanced spend controls on consultancy, communications and digital spend are in place.
Risk to successful office move that internet connectivity may not be in place for current planned move in date. | 3 | 3 | 9 | Risk is being mitigated by go/no go decision on office move date, potential use of NHS England's Wi-Fi in building, and staff working from home.
Very low
Low
Medium
High
Very high

## Slide 14: Brilliant Organisation: High-level summary of performance
NICE Business plan KPIs | Actual YTD | KPI Performance target 24-25 | KPI starting Performance 23-24 | % Increase vs 23-24
Media coverage of NICE that is positive in sentiment | 90% | 80% | 80% | 10+ percentage points (pp)
Media coverage that is generated by NICE includes at least one NICE key message | 55% | 60% | 54% | 1+ pp
Representation of ethnic minority, disabled and LGBTQ+ colleagues at all levels | Ethnic 19.6% Disabled 10.1% LGBTQ+ 8.5% | Ethnic 20.3% Disabled 10.44% LGBTQ+ 9.17% | Ethnic 18.21​% Disabled​ 9.49% LGBTQ+​ 8.34% | +1.2pp +0.4pp +0.2pp
Number of informal resolutions | 13 | 31 (50% increase) | 21 | +86%*
Financial position (deficit and surplus)** | £1.9m surplus YTD | No deficit, Surplus <£1m | No deficit, Surplus <£1m (Achieved) | 
NICE Bus Plan Milestones | Due Date | RAG
Launched a new Equality, Diversity and Inclusion Roadmap including new objectives to improve staff experience and representation | Q1 | C
Rolled out Power-BI enabled detailed financial forecasting and scenario planning to increase accuracy of forecasts and engage operational teams | Q2 | G
Fully embedded finance business partnering to improve financial input into directorate decisions | Q3 | G
Completed a successful office move to our new Manchester office | Q3 | A
Leadership competencies implemented with initial review and feedback provided for all leadership teams | Q3 | A
RAG rating key: C= complete; G= green; A= amber; R= red
* Based on number achieved in 4 months compared to average 23-24 trajectory of 1.75 per month
** Figures as of 31 August 2024
Notes on RAG status:
The KPI is amber due to a strong performance for TA/HST cost recovery and a higher than planned vacancy rate, meaning NICE is £1.9m under plan at end of month 5. However, the impact of the pay award (funding TBC), a possible 2% budget reduction and liabilities associated with the Manchester office move will likely bring the surplus closer to £1m by year-end.
Risk that the technology may not be ready to use on first day of relocation due to third party suppliers
Delay in confirming the exact format of the leadership development programme
1
2
1
2
3
3
RAG rating key: C= complete; G= green; A= amber; R= red
All figures as of 31 July 2024 unless otherwise stated

## Slide 15: Appendix to Brilliant organisation
 | YTD | Target | Comparator/ baseline | % improvement or decrease | Add comment why target not met: provide reason, anticipated publication date/month | RAG
Sickness rate - overall | 2.75% | 3% | 3% | 0.83pp below baseline | Target being achieved | G
Total turnover rate | 12.16% | N/A | 10% | 2.16pp above baseline | Showing a gradual decrease month by month. | N/A
Voluntary turnover | 7.77% | N/A | No baseline |  | Showing a decline month by month to July 2024. | N/A
Non voluntary turnover | 4.39% | N/A | No baseline |  | Remaining static, given the MoC exercises carried out and the phasing of notice periods. | N/A
FOIs | 95% | 90% of FOIs responded to with 20 working days | 90% | 5pp improvement | Target being exceeded | G
Parliamentary questions | 100% | 90% of Parliamentary Questions responded to within the requested time frame | 90% | 10pp improvement | Target being exceeded | G
Payment compliance | 97.5% | 95% of invoices paid within 30 days of calendar month-end | 96% | 1.5pp improvement | Target achievement continues. | G
Complaints | N/A | 80% of complaints acknowledged and responded to within 20 working days | 100% | N/A | No complaints received and due for response. | G
RAG rating key: C= complete; G= green; A= amber; R= Red
All figures as of 31 July 2024 unless otherwise stated

## Slide 16: Financial performance as of 31 August 24
Year to date financial performance
As at the end of August we are underspent by £1.9m against budget. The underspend is driven by (1) Pay: actual vacancy rate of c8% vs. planned vacancy factor of 2.5%; (2) reserves not being drawn against year to-date and contingency not being utilised; and (3) higher income from TA-HST programme.
Full year forecast
The current forecast outturn underspend of £1.15m includes assumptions about material expenditure in several areas, additional funding and planned efficiency savings.
Pay - currently underspent because of vacancies, the impact of the 5.5% pay award (payable in the latter half of the year) is £2.5m greater than the planning assumption of a 2% rise. This means that pay is currently forecasting an overspend against budget; however, some funding is expected to follow (shown as TBC as part of funding adjustments).
Non-pay - overspend of £2m is mainly due to costs and liabilities associated with the Manchester office move.
Income - over-recovery is being driven by improvement in performance of the TA-HST programme.
The second table sets out the risk and uncertainty around the assumptions built into the forecast and the potential ranges in an up/downside scenario. If these costs do not materialise, there is a risk of a material underspend.
Full year forecast - scenarios
Spend category | YTD budget £000 | YTD actual £000 | YTD Variance £000 | Annual budget £000 | Estimated outturn £000 | Estimated outturn variance £000
Pay | 24,797 | 23,741 | (1,055) | 61,198 | 61,741 | 542
Non-Pay | 9,995 | 9,913 | (82) | 27,158 | 29,206 | 2,049
Income | (11,242) | (12,037) | (795) | (27,135) | (29,321) | (2,186)
Total - baseline | 23,549 | 21,618 | (1,931) | 61,221 | 61,626 | 405
TBC: Funding adjustments |  |  |  | 1,550 | 0 | (1,550)
Total - adjusted baseline | 23,549 | 21,618 | (1,931) | 62,771 | 61,626 | (1,145)
Uncertainties / Opportunities | Worst-case FOT (£m) | Best-case FOT (£m) | Comments
Month 5 FOT (most-likely) | (1.15) | (1.15) | Most-likely scenario (per table above)
Office move costs & liabilities | 0.40 | (1.00) | Forecast outturn assumes £2m costs associated with the office move. In the best-case scenario this could drop to £1m.
TA-HST programme income | 0.40 | (0.70) | Forecast assumes the most-likely income is £13.7m income, but possible range is between £13.3m and £14.4m.
Tech Debt / Contingent Labour | 0 | (0.30) | Tech Debt cost brought forward from planned 25/26. Contingent labour to cover sickness and gaps in staffing. Best-case assumed slippage on forecast spend.
Timeliness Programme | 0 | (0.60) | Forecast assumes all the funding approved and assigned for this work will be spent but there may be some slippage.
Deficit / (Surplus) - Range | (0.35) | (3.75) | 

## Slide 17: Headline description of key projects to deliver NICE aims
NICE aim | Project name | Project headline description
Timely and High-Quality Guidance | Rules Based Pathway (RBP) | Establishing the rules and principles on which NICE and NHS England will work in partnership to evaluate, commission and fund medical technologies
 | Improving Timeliness and Staff experience (ITSE) | Improved timeliness by standardising and improving processes across guidance producing centres, through the use of digital tools and continuous improvement approaches
 | Incorporation of TAs into guidelines | Inclusion of medicines and healthtech recommendations within guidelines to make NICE guidance more useful and useable
Useable | Content governance and structured recommendations | Revise the governance used to write all guidance products so are centred around users. Create more actionable, structured recommendations across different types of guidance to benefit users.
 | Knowledge platform | Procure and implement knowledge platform which structured content will be migrated to.
Impactful | Measurement uptake | Measure uptake of our guidance and use that data to ensure NICE focuses on our priorities.
 | Amplify priority partnerships | Work closely with critical stakeholders who can amplify our guidance in priority areas to help get the best care to patients fast.
 | Targeted implementation support | We will use implementation science to focus on system priorities populations with identified health in equalities and other areas that matter most to people and communities.
 | Public involvement best practice approach | Implementing a new way to reach the right members of the public at the right time in the right way to increase uptake of guidance and support getting the best care to people fast.
 | Implementation support toolkits | Development of comprehensive implementation support toolkits where implementation challenges already exist or are anticipated