## Public board meeting action log
Action ref | Board meeting | Item reference | Action | Owner | Target completion | Latest update | Status | Date closed
22/30 | 2022-12-16 | 7 | CPO to outline their perspective on what more NICE could do to reduce turnover, drawing on good practice elsewhere. | HB | 2023-09-01 | A briefing has been prepared and will be circulated to the Board following review by ET. | Open | n/a
22/31 | 2022-12-16 | 8 | Impact of using the existing flexibilities to adopt a broader societal perspective to be kept under review; with the Board receiving a progress update, including information on when a wider perspective has impacted recommendations, at a suitable future date. | NC | 2023-12-01 | Update scheduled for December 2023 Board meeting. | Open | n/a
22/32 | 2022-12-16 | 9 | Board to be kept informed of the impact of the health inequalities initiatives on the committees’ work and how NICE’s activities are impacting other health and care organisations. | CM | 2023-12-01 | Update scheduled for December 2023 Board meeting. | Open | n/a
23/06 | 2023-03-22 | 7 | Report on the first year of implementation of the updated CHTE manual to include information on how the severity modifier has been applied, including for which conditions; information on the utilisation of the flexibilities around health inequalities; and the outcome of the work on committee consistency. | HK | 2023-12-01 | Update scheduled for December 2023 Board meeting. | Open | n/a
23/09 | 2023-05-17 | 8 | Report on the pay gap for disabled and ethnic minority staff. | HB | 2023-09-01 | Included in the annual equality report to the September Board meeting and will also be provided alongside future gender pay reporting. | Closed | 2023-09-21
23/10 | 2023-05-17 | 9 | Board to receive an update on the plans to update the NICE Principles to guide how NICE can align environmental sustainability to its core remit. | FG | 2024-03-01 | Scheduled for March 2024 Board meeting. | Open | n/a
23/12 | 2023-07-19 | 6 | Future performance reports to show the number of topics used to calculate the mean for the medicines timeliness KPIs. In addition, a qualitative analysis of the factors affecting the timeliness of TA guidance to be provided at a suitable point in the future | HK | 2023-09-01 | Performance report amended to show the number of topics used to calculate the medicines timeliness KPIs, and also a breakdown of the primary cause of delays. | Closed | 2023-09-21
23/14 | 2023-07-19 | 6 | September Board meeting to receive an update on the analysis of the factors behind the under-recovery of TA income and the mitigations. | HK/BS | 2023-09-01 | Update provided to the September Board seminar | Closed | 2023-09-21
23/15 | 2023-07-19 | 8 | Board to receive a further progress update on talent management in 6 months. | HB | 2023-11-01 | Further updates will be provided to the Remuneration Committee in November 2023 and June 2024. | Closed | 2023-09-21
23/16 | 2023-07-19 | 8 | Updated appraisal form to be provided to the NEDs for information. | HB | 2023-09-01 | Complete. | Closed | 2023-09-21